## 3 Week Look Ahead
[5 empty] | 3 Week Look Ahead | [14 empty] | Data Date : 09/01/2025
Activity ID | Activity Name | Start | Finish | Duration (Workdays) | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22
Lincoln High School - LIVE FILE - TRUE LIVE FILE
Overall Project
Milestones
MS15 - Beneficial Occupancies
10-10033 | Auditorium Occupancy Phase 2 Summer 2025 | 2025-09-02 | 2025-09-02 | 0.71429
Pinner Costs
Allowances
AD-03 | ADA-03 - ACCM Asphalt Abatement & Removal | 2023-06-01 | 2025-09-01 | 588.5714
T-508 | Pkg 5 Track & Field, Added Design & Constr. Fees | 2023-06-26 | 2025-09-01 | 570.7143
T-642 | Pkg 2 CD 73 Furnish DW & SS at N concession stand | 2025-02-25 | 2025-09-01 | 135
T-528 | DD 018 Lighting Control nLights - Construction Costs | 2024-06-01 | 2025-09-02 | 327.8571
T-677 | De-scope of Countertop and Removal of Pre-Installed Attachment Brackets | 2025-03-31 | 2025-09-03 | 112.1429
T-621 | Pkg5 DBD29 Scoreboard Relocation Construction Fees | 2025-09-01 | 2025-09-05 | 3.5714
T-662 | Install Outdoor Horticultural Sink (Design | 2025-09-01 | 2025-09-05 | 3.5714
T-663 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-664 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-665 | Provide Electronic Door Lockset at B-217 | 2025-09-01 | 2025-09-05 | 3.5714
T-666 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-667 | Countertop Descope | 2025-09-01 | 2025-09-05 | 3.5714
T-669 | Additional Abatement at Administration Building | 2025-09-01 | 2025-09-05 | 3.5714
T-670 | Additional Abatement at Gymnasium Building | 2025-09-01 | 2025-09-05 | 3.5714
T-671 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-675 | Pkg 1 CD127 Remove RAW at B-33 | 2025-09-01 | 2025-09-05 | 3.5714
T-678 | Washer Dryer and Utility Sink | 2025-09-01 | 2025-09-05 | 3.5714
T-679 | VOID(T-681) | 2025-09-01 | 2025-09-05 | 3.5714
T-680 | Update Graphic Package | 2025-09-01 | 2025-09-05 | 3.5714
T-681 | Geo-Textile Fabric_Home Ec_ | 2025-09-01 | 2025-09-05 | 3.5714
T-682 | Existing Storage Container Relocation PKG 5 | 2025-09-01 | 2025-09-05 | 3.5714
T-683 | Pkg 9 CD128 Duct Leakage Repair | 2025-09-01 | 2025-09-05 | 3.5714
T-684 | Basement Door Changes | 2025-09-01 | 2025-09-05 | 3.5714
T-685 | Replace Current Chain Link by HOMEC Building | 2025-09-01 | 2025-09-05 | 3.5714
T-686 | Remove Video Dome Camera from Elev. Cab | 2025-09-01 | 2025-09-05 | 3.5714
T-687 | Provide and Install 1 New Storage Container | 2025-09-01 | 2025-09-05 | 3.5714
T-688 | Relocate Player Benches from East Plateau | 2025-09-01 | 2025-09-05 | 3.5714
T-690 | A/E Services for Change in Refrigerant for PKG 13 | 2025-09-01 | 2025-09-05 | 3.5714
T-692 | A/E Service for New Picket Fence on Package 7 | 2025-09-01 | 2025-09-05 | 3.5714
T-694 | Addt'l Fencing and Gates | 2025-09-01 | 2025-09-05 | 3.5714
T-691 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-695 | PKG 9 Repair Audit. (E) HVAC duct damages | 2025-09-01 | 2025-09-05 | 3.5714
T-697 | PKG 7, 14 DBD24 Curtain Wall WAter/Air Testing | 2025-09-01 | 2025-09-05 | 3.5714
T-698 | ADA Card Service | 2025-09-01 | 2025-09-05 | 3.5714
T-700 | Dispose Pavers, Concrete Benches | 2025-09-01 | 2025-09-05 | 3.5714
T-693 | Additional Security Screen | 2025-09-01 | 2025-09-05 | 3.5714
Construction Schedule
CS-1002 | COST-CPM Schedule Monthly Update (Construction) - Package 1 | 2022-06-13 | 2025-09-02 | 841.4286
CS-1005 | Approved CPM Schedule - Package 14 | 2023-06-01 | 2025-09-03 | 590
Environmental Import/Export Material Testing
ET-1001 | COST-Environmental Soils Testing - Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
Overhead, Construction Facilities & Temp. Controls
Package 1
PH1-101 | COST-Insurance - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-102 | COST-DB Project Manager - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-103 | COST-Project Manager - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-104 | COST-General Superintendent - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-105 | COST-Safety Manager - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-106 | COST-Additional Project Staff - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-107 | COST-Quality Control - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-108 | COST-BIM - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-109 | COST-Site Temp Fencing - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-112 | COST-Vehicle/Fuel - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-113 | COST-Field Office Rental - IOR (Monthly) - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-114 | COST-Field Office Rental - LAUSD/PEX (Monthly) - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-115 | COST-Field Office Rental - Pinner (Monthly) - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-116 | COST-Home Office - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-117 | COST-Permits - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-118 | COST-Temporary Electric - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-119 | COST-Temporary Water - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-120 | COST-Temporary Toilets - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-121 | COST-Traffic Control - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-122 | COST-Security - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-123 | COST-Interim Cleanup - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-124 | COST-Final Cleanup - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-125 | COST-Equipment Repair/Small Tools/Tool Shed/Safety - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-126 | COST-Dust Control - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-127 | COST-Project Record Documents/As-Builts - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-129 | COST-Dumpsters - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
Package 4
PH4-201 | COST-Insurance - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-202 | COST-DB Project Manager - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-203 | COST-Project Manager - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-204 | COST-General Superintendent - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-205 | COST-Safety Manager - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-206 | COST-Additional Project Staff - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-207 | COST-Quality Control - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-208 | COST-BIM - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-209 | COST-Site Temp Fencing - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-210 | COST-Office Furniture & Equipment/Supplies - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-211 | COST-Vehicle/Fuel - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-212 | COST-Field Office Rental - IOR (Monthly) - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-213 | COST-Field Office Rental - LAUSD/PEX (Monthly) - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-214 | COST-Field Office Rental - Pinner (Monthly) - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-215 | COST-Home Office - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-216 | COST-Permits - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-217 | COST-Temporary Electric - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-218 | COST-Temporary Water - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-219 | COST-Temporary Toilets - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-220 | COST-Traffic Control - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-221 | COST-Security - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-222 | COST-Interim Cleanup - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-223 | COST-Final Cleanup - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-224 | COST-Equipment Repair/Small Tools/Tool Shed/Safety - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-225 | COST-Dust Control - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-226 | COST-Project Record Documents/As-Builts - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-227 | COST-Closeout Documents - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-228 | COST-Dumpsters - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
Package 6
13-P6010 | Monthly Rental - Interim Housing - West Campus | 2025-09-03 | 2027-04-21 | 425.7143
23-P6010 | Monthly Interim Housing Air Filter Replacement | 2025-09-03 | 2027-04-21 | 425.7143
General Conditions
GC-1003 | COST-Package 1: Fee | 2022-06-13 | 2025-09-03 | 842.1429
GC-1012 | 4-4: Historic Stair Replacement - Package 5: CA Services - Alternates | 2023-07-18 | 2025-09-03 | 556.4286
GC-1004 | COST-Package 4: Fee | 2023-03-06 | 2025-09-06 | 654.2857
GC-1008 | COST-4-2: Teacher Shuttle - Package 4 - Alternates | 2023-03-06 | 2025-09-06 | 654.2857
Field Engineering
FE-1002 | COST-Field Engineering/Survey - Package 4 | 2023-03-06 | 2025-09-05 | 653.5714
SWPPP
PH1-130 | COST-Implement SWPPP - Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
PH1-131 | COST-SWPPP Maintenance - Duration of Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
PH4-229 | COST-Implement SWPPP - Package 4 | 2023-03-06 | 2025-09-05 | 653.5714
PH4-230 | COST-SWPPP Maintenance - Duration of Package 4 | 2023-03-06 | 2025-09-05 | 653.5714
Contract Closeout
PH1-132 | COST-Punchlist - Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
PH4-231 | COST-Punchlist - Package 4 | 2023-07-18 | 2025-09-05 | 557.8571
Package 2 (P2) - Field House, DWP, Batting Cages
P2 - Construction
Package 2 - Construct New FieldHouse
Site Work
Utilities
Underground Infrastructure
33-9424 | Wire Pulled -Pk2.NFH.Elec - 800 Bldg to DWP Yard - NS | 2024-01-02 | 2025-09-02 | 435.7143
33-9968 | Inspections -Pk2.NFH.Elec - 800 Bldg to DWP Yard | 2024-07-23 | 2025-09-02 | 290.7143
Package 5 (P5) - East Campus Ramps, Historical Stairs, Elevator Tower
P5 - Construction
Package 5 - Historical Stair - Alternate 4
Electrical
26-5502 | Set Poles -Pk5-HistStr-Elec | 2025-09-02 | 2025-09-09 | 5.7143
26-5503 | Pull Wire -Pk5-HistStr-Elec | 2025-09-10 | 2025-09-16 | 5
26-5504 | Terminate Light Poles -Pk5-HistStr-Elec | 2025-09-10 | 2025-09-16 | 5
Final Sign-offs
26-9475 | JHA Elect Final -Pk5-HistStr | 2025-09-17 | 2025-09-30 | 10
01-9009 | Final Signoffs -Pk5-HistStr | 2025-09-17 | 2025-09-30 | 10
Package 6 (P6) - Interim Housing 1-B, Locker Room, Admin
P6 - Construction
Interim Housing B - West Campus
13-3742 | Set Portables - West Campus (Installation over 3 Saturdays) | 2025-08-26 | 2025-09-02 | 5.7143
22-9125 | Install DCW Shut-Off Valve, Cleanout & Yard Box - West Campus | 2024-12-18 | 2025-09-02 | 185
32-10225 | AC Overlay Ramp Toe - West Campus | 2025-09-03 | 2025-09-04 | 1.4286
13-3752 | Set Handrails - West Campus | 2025-09-05 | 2025-09-08 | 2.8571
26-9594 | Final Electrical Connections to Units - West Campus | 2025-09-03 | 2025-09-09 | 5
27-10521 | LV Mobilization - West Campus | 2025-09-10 | 2025-09-10 | 0.71429
10-10073 | Signage - West Campus | 2025-09-09 | 2025-09-11 | 2.1429
22-9145 | Install Drinking Fountains - West Campus | 2025-09-09 | 2025-09-11 | 2.1429
22-9135 | Install Condensate & Connect to Existing Utility - West Campus | 2025-09-10 | 2025-09-12 | 2.1429
05-9390 | DF Rails - West Campus | 2025-09-12 | 2025-09-15 | 2.8571
28-10600 | Fire Alarm Trim - West Campus | 2025-09-09 | 2025-09-15 | 5
27-10471 | Converged IP Device Install - West Campus | 2025-09-09 | 2025-09-15 | 5
27-10481 | AV Cabling - West Campus | 2025-09-09 | 2025-09-15 | 5
28-10610 | Security Cable Rough-in - West Campus | 2025-09-09 | 2025-09-15 | 5
22-9155 | Connect DW & SS to Units - West Campus | 2025-09-10 | 2025-09-16 | 5
32-10235 | Set / Install Fence - West Campus | 2025-09-10 | 2025-09-16 | 5
26-9584 | Set Mounted Lights - West Campus | 2025-09-10 | 2025-09-16 | 5
27-10531 | LV Horizontal Copper Rough-in - West Campus | 2025-09-10 | 2025-09-16 | 5
27-P6040 | LV Copper/Fiber Backbone Terminations & Testing - West Campus | 2025-09-10 | 2025-09-16 | 5
26-9604 | Run Elec Conduit to Ext Lts & Terminate - West Campus | 2025-09-10 | 2025-09-18 | 6.4286
12-8022 | Window Blinds - West Campus | 2025-09-16 | 2025-09-22 | 5
28-10620 | Security Device Install - West Campus | 2025-09-16 | 2025-09-22 | 5
27-10491 | Converged IP Testing/Commissioning - West Campus | 2025-09-16 | 2025-09-22 | 5
27-10501 | AV Trim and Device Install - West Campus | 2025-09-16 | 2025-09-22 | 5
32-10245 | Set Gates - West Campus | 2025-09-17 | 2025-09-23 | 5
27-10541 | LV IDF/LDF Buildout - West Campus | 2025-09-16 | 2025-09-29 | 10
13-3762 | Set FF&E - West Campus | 2025-09-17 | 2025-09-30 | 10
10-P6010 | Toilet Accessories - West Campus | 2025-09-17 | 2025-09-30 | 10
Install Interim Locker Rooms at Tennis Courts
East Campus - Locker Room Portables
12-P6010 | Window Blinds - West Campus | 2025-09-02 | 2025-09-08 | 5
Package 7 (P7) - Performing Arts
P7 - Submittals
Package 7 - Bldg J -Perf. Arts
Submittals
Roller Window Shades - 122413
12-8082 | Fabricate - 122413 - Pkg 7 | 2025-06-20 | 2025-09-04 | 55
Planting - 329000
32-4527 | Prepare and Submit to LAUSD - 329000 - Pkg 7 | 2024-01-02 | 2025-09-02 | 435.7143
32-4528 | LAUSD Review & App'l - 329000 - Pkg 7 | 2025-09-03 | 2025-09-16 | 10
32-10385 | Fabricate - 329000 - Pkg 7 | 2025-09-17 | 2025-10-13 | 19.2857
P7 - Construction
Package 7 - Construct New Performing Arts Building
Roof
01-2469 | Punch -Pk7-Rf | 2025-09-02 | 2025-09-15 | 10
Interiors
Basement
Corridor
01-9115 | Modified Tecum Panel Finishes-LBCorr-Pk7-Int | 2025-09-02 | 2025-09-12 | 7.8571
01-2389 | Final Clean Up -LBCorr-Pk7-Int | 2025-09-15 | 2025-09-17 | 2.1429
01-2470 | Punch -LBCorr-Pk7-Int | 2025-09-15 | 2025-09-17 | 2.1429
IDF Room
27-7018 | Testing/Commissioning | 2025-08-28 | 2025-09-22 | 18.5714
27-7020 | Testing/Commissioning | 2025-08-28 | 2025-09-22 | 18.5714
Interior - Flex Drama / Storage
01-2471 | Punch -FlexD-Pk7-Int | 2025-09-02 | 2025-09-04 | 2.1429
Interior - Computer Lab
01-2489 | Final Clean Up -Comp-Pk7-Int | 2025-09-15 | 2025-09-17 | 2.1429
01-2495 | Punch -Comp-Pk7-Int | 2025-09-18 | 2025-09-22 | 3.5714
Elevator Machine Room
01-2383 | Final Clean Up -EMR-Pk7-Int | 2025-09-15 | 2025-09-15 | 0.71429
Elevator
14-2672 | Schedule Elevator Inspector -Elev-Pk7-Int | 2025-09-16 | 2025-09-18 | 2.1429
14-2673 | Elevator Inspection -Elev-Pk7-Int | 2025-09-19 | 2025-09-19 | 0.71429
01-2468 | Punch -Elev-Pk7-Int | 2025-09-22 | 2025-09-24 | 2.1429
Level 1
Corridor
09-5555 | Final Paint -L1Corr-Pk7-Int | 2025-09-02 | 2025-09-04 | 2.1429
10-3665 | Fire Ext & Cabs -L1Corr-Pk7-Int | 2025-09-02 | 2025-09-04 | 2.1429
10-3700 | Janitor Closet Mop Racks -L1-Pk7-Int | 2025-09-05 | 2025-09-05 | 0.71429
10-3667 | Corner Guards -L1Corr-Pk7-Int | 2025-09-05 | 2025-09-09 | 3.5714
01-2523 | Final Clean Up -L1Corr-Pk7-Int | 2025-09-10 | 2025-09-12 | 2.1429
01-2530 | Punch -L1Corr-Pk7-Int | 2025-09-10 | 2025-09-12 | 2.1429
Restrooms
10-3669 | Toilet Accs -Pk7.L1.RR | 2025-09-02 | 2025-09-04 | 2.1429
09-5576 | Final Paint -Pk7.L1.RR | 2025-08-27 | 2025-09-05 | 7.1429
01-2535 | Final Clean Up -Pk7.L1.RR | 2025-09-05 | 2025-09-09 | 3.5714
26-4853 | Intrusion Devices -Pk7.L1.RR | 2025-09-05 | 2025-09-09 | 3.5714
01-2541 | Punch -Pk7.L1.RR | 2025-09-10 | 2025-09-12 | 2.1429
Interior - Media CR / Storage
09-5536 | Final Paint -Pk7.L1.Media | 2025-09-05 | 2025-09-09 | 3.5714
12-3231 | Roller Shades -Pk7.L1.Media | 2025-09-10 | 2025-09-12 | 2.1429
01-2542 | FF&E -Pk7.L1.Media | 2025-09-10 | 2025-09-12 | 2.1429
01-2511 | Final Clean Up -Pk7.L1.Media | 2025-09-15 | 2025-09-17 | 2.1429
11-7003 | Install Divider Curtain -Pk7.L1.Media | 2025-09-15 | 2025-09-19 | 3.5714
01-2531 | Punch -Pk7.L1.Media | 2025-09-22 | 2025-09-24 | 2.1429
Exterior
North Elevation
Framing
07-3258 | Seismic Joints -Pk7.North.Framing | 2025-03-20 | 2025-09-03 | 120
Site Work
Walls / Pads / Misc Concrete
Ramp - North
05-7777 | Install Guardrail -Ramp-Pk7-StWk | 2025-09-16 | 2025-09-22 | 5
Fence / Gate
32-4554 | Dig Fence/Gate Holes -Pk7-StFin - Pending CCD | 2025-08-18 | 2025-09-12 | 18.5714
32-4555 | Set Fence/Gate Posts -Pk7-StFin | 2025-08-20 | 2025-09-19 | 22.1429
32-4556 | Pour Fence/Gate Ftgs -Pk7-StFin | 2025-08-22 | 2025-09-19 | 20.7143
Canopy
32-7061 | Set Canopy Steel | 2025-09-11 | 2025-09-11 | 0.71429
32-7071 | Weld Conopy Steel | 2025-09-12 | 2025-09-17 | 4.2857
07-7121 | Install Canopy Decking | 2025-09-18 | 2025-09-22 | 3.5714
Finishes
27-4174 | Exterior Low Voltage Trim Pk7-SiteFin | 2025-08-27 | 2025-09-03 | 5.7143
28-3551 | Exterior Fire Alarm Trim Pk7-SiteFin | 2025-08-27 | 2025-09-03 | 5.7143
32-4580 | Set Gate Pk7-SiteFin | 2025-09-22 | 2025-09-26 | 3.5714
32-4599 | Install Fencing Pk7-SiteFin | 2025-09-22 | 2025-09-26 | 3.5714
Testing / Sign-offs
Fire Alarm & Fire Sprinkler
28-3543 | NFPA 13 & 24 Testing-FA | 2025-09-04 | 2025-09-15 | 8.5714
28-3545 | NFPA 72 Testing-FA | 2025-09-16 | 2025-09-19 | 2.8571
Domestic Water
22-2795 | Bleed/Flush/Sanitize Risers-DWtr | 2025-09-02 | 2025-09-08 | 5
22-2794 | Hook up Fixt-DWtr | 2025-02-28 | 2025-09-11 | 140
22-2793 | Flush & Chlorination Test-DWtr | 2025-09-12 | 2025-09-18 | 5
22-7999 | Lead Test-DWtr | 2025-09-19 | 2025-09-25 | 5
Final Sign-offs & Commissioning
26-4663 | JHA Elect Final -Pk7-Final | 2025-09-02 | 2025-09-08 | 5
01-7002 | Develop Asset Workbook (MAC Addresses) -Pk7-Final | 2025-09-02 | 2025-09-08 | 5
01-7003 | FTPMG Programming -Pk7-Final | 2025-09-09 | 2025-09-10 | 1.4286
01-2396 | FD Final Signoff -Pk7-Final | 2025-09-19 | 2025-09-19 | 0.71429
22-2798 | JHA Plum Final -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
01-7004 | Commissioning -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
28-8003 | Programming and Commissioning -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
28-8004 | Closeout Documentation -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
Package 8 (P8) - Music, Federal Building Barrier Removal
P8 - Construction
Package 8 - Auditorium Barrier Removal
Finishes Phase 2 (Summer 2025)
28-8027 | Closeout Documentation | 2025-09-02 | 2025-09-15 | 10
27-8010 | Closeout Documentation | 2025-07-09 | 2025-09-17 | 50.7143
Package 8 - Partial Modernize Federal Building
12-8002 | Install (N) Window Coveing-Pk8-Federal | 2025-09-02 | 2025-09-03 | 1.4286
05-8001 | Cane Detectable Rails -Pk8-Federal | 2025-09-02 | 2025-09-03 | 1.4286
01-8004 | Walk/ Acceptance/ADA -Pk8-Federal | 2025-09-04 | 2025-09-08 | 3.5714
28-8024 | Closeout Documentation | 2025-09-02 | 2025-09-08 | 5
Package 8 - Partial Modernize Music Building
01-8001 | Final Commissioning / Pre Functional Testing -Pk8-Music | 2025-09-02 | 2025-09-02 | 0.71429
01-8002 | Walk/ Acceptance/ADA -Pk8-Music | 2025-09-02 | 2025-09-02 | 0.71429
28-10630 | Closeout Documentation | 2025-09-02 | 2025-09-03 | 1.4286
Package 9 (P9) - Mini Plant HVAC
P9 - Construction
Package 9 - Mini Plant HVAC
Exterior
Mech Yard Upgrades
01-9001 | Punch -Yard-Pk9-Ext | 2025-09-08 | 2025-09-12 | 3.5714
Testing / Sign-offs
HVAC
Start Up/ TAB
23-9232 | TAB Review -TAB | 2025-08-07 | 2025-09-09 | 24.2857
23-9236 | Commission Complete -TAB | 2025-09-12 | 2025-09-12 | 0.71429
Final Sign-offs & Commissioning
22-9077 | JHA Plum Final -Pk9.Final | 2025-09-02 | 2025-09-08 | 5
26-9473 | JHA Elect Final -Pk9.Final | 2025-09-02 | 2025-09-08 | 5
23-9239 | Generate Trend Report | 2025-08-28 | 2025-09-12 | 11.4286
01-7320 | Commissioning -Pk9.Final | 2025-08-28 | 2025-09-12 | 11.4286
01-9005 | Commissioning Report Review/App'l -Pk9.Final | 2025-08-06 | 2025-09-12 | 27.1429
01-7314 | OEHS Pre- Walk -Pk9.Final | 2025-09-15 | 2025-09-15 | 0.71429
01-9003 | Punchlist Corrections -Pk9.Final | 2025-08-07 | 2025-09-15 | 28.5714
01-9004 | OEHS Final -Pk9.Final | 2025-09-16 | 2025-09-22 | 5
01-9006 | 100% PSR & OEHS Occ. Sign-Off -Pk9.Final | 2025-09-16 | 2025-09-22 | 5
Package 10 (P10) - Home Economis, Servery Kiosk Bldg #14
P10 - Submittals
Package 10 - Building B Home Ec, IP Converge & Entry Plaza
Submittals
Installing the Needle Strip Bird Deterrent System on Horizontal Projecting Surfaces - 10296-02
10-10323 | Fabricate - 10296-02 - Pkg 10 | 2025-08-11 | 2025-09-11 | 22.8571
Planting - 329000
32-4404 | LAUSD Review & App'l - 329000 - Pkg 10 | 2024-02-17 | 2025-09-11 | 409.2857
32-10405 | Fabrication - 329000 - Pkg 10 | 2025-09-12 | 2025-09-13 | 1.4286
P10 - Construction
Package 10 - Modernize Home Economics
Treatment of Historic Finishes
10-3102 | Replace Bird Deterrents -West-Pk10-Hist | 2025-09-19 | 2025-09-22 | 2.8571
Interiors
Level 1
Corridor
Clean/Punch/Commission
01-2201 | Final Clean Up -L1-Pk10-Corr | 2025-09-15 | 2025-09-19 | 3.5714
01-2282 | Punch -L1-Pk10-Corr | 2025-09-22 | 2025-09-26 | 3.5714
Finishes
12-3129 | Install Window Blinds -L1-Pk10-Corr | 2025-09-02 | 2025-09-08 | 5
Restrooms
Clean/Punch/Commission
01-2287 | Final Clean Up -L1-Pk10-RR | 2025-09-15 | 2025-09-19 | 3.5714
01-2293 | Punch -L1-Pk10-RR | 2025-09-22 | 2025-09-26 | 3.5714
Interior - West Bldg (GL A-L, 6-10)
Clean/Punch/Commission
01-2189 | Final Clean Up -L1-Pk10-West | 2025-09-15 | 2025-09-19 | 3.5714
01-2283 | Punch -L1-Pk10-West | 2025-09-22 | 2025-09-26 | 3.5714
Specialties / Equipment
12-3126 | Install Window Blinds -L1-Pk10-West | 2025-09-02 | 2025-09-08 | 5
01-2294 | FF&E -L1-Pk10-West | 2025-09-15 | 2025-09-19 | 3.5714
Interior - East Bldg - North (GL 1-6, K-Q)
Specialties
12-3166 | Install Window Blinds -L1-Pk10-NE | 2025-09-02 | 2025-09-08 | 5
01-2311 | FF&E -L1-Pk10-NE | 2025-09-15 | 2025-09-19 | 3.5714
Clean/Punch/Commission
01-2301 | Final Clean Up -L1-Pk10-NE | 2025-09-15 | 2025-09-19 | 3.5714
01-2307 | Punch -L1-Pk10-NE | 2025-09-22 | 2025-09-26 | 3.5714
Interior - East Bldg - South (GL L-R, 6-10)
Specialties
01-2322 | FF&E -L1-Pk10-SE | 2025-09-15 | 2025-09-19 | 3.5714
Clean/Punch/Commission
01-2312 | Final Clean Up -L1-Pk10-SE | 2025-09-15 | 2025-09-19 | 3.5714
01-2318 | Punch -L1-Pk10-SE | 2025-09-22 | 2025-09-26 | 3.5714
Level 2
Corridor
Frame Ceiling and MEP Drops
09-9609 | Seismic Bracing Installation -L2-Pk10-Corr | 2025-08-13 | 2025-09-02 | 15
Ceiling Finishes
09-5318 | Ceiling Tiles -L2-Pk10-Corr | 2025-06-26 | 2025-09-02 | 49.2857
Equipment/Furnishings
14-2816 | Install Wheelchair Lift -L2-Pk10-Corr | 2025-09-03 | 2025-09-16 | 10
Clean/Punch/Commission
01-2335 | Final Clean Up -L2-Pk10-Corr | 2025-09-15 | 2025-09-19 | 3.5714
01-2342 | Punch -L2-Pk10-Corr | 2025-09-22 | 2025-09-26 | 3.5714
Restrooms
Clean/Punch/Commission
01-2347 | Final Clean Up -L2-Pk10-RR | 2025-09-15 | 2025-09-19 | 3.5714
01-2353 | Punch -L2-Pk10-RR | 2025-09-22 | 2025-09-26 | 3.5714
Interior - West Bldg (GL A-L, 6-10)
Specialties
01-2354 | FF&E -L2-Pk10-West | 2025-09-02 | 2025-09-08 | 5
Clean/Punch/Commission
01-2323 | Final Clean Up -L2-Pk10-West | 2025-09-15 | 2025-09-19 | 3.5714
01-2343 | Punch -L2-Pk10-West | 2025-09-22 | 2025-09-26 | 3.5714
Interior - East Bldg North (GL 1-6, K-Q)
Equipment/Furnishings
12-3177 | Install Window Blinds -L2-Pk10-NE | 2025-09-02 | 2025-09-08 | 5
Specialties
01-2365 | FF&E -L2-Pk10-NE | 2025-09-02 | 2025-09-08 | 5
Clean/Punch/Commission
01-2355 | Final Clean Up -L2-Pk10-NE | 2025-09-15 | 2025-09-19 | 3.5714
01-2361 | Punch -L2-Pk10-NE | 2025-09-22 | 2025-09-26 | 3.5714
Interior - East Bldg South (GL L-R, 6-10)
Equipment/Furnishings
12-3180 | Install Window Blinds -L2-Pk10-SE | 2025-09-02 | 2025-09-08 | 5
Specialties
01-2376 | FF&E -L2-Pk10-SE | 2025-09-02 | 2025-09-08 | 5
Clean/Punch/Commission
01-2366 | Final Clean Up -L2-Pk10-SE | 2025-09-15 | 2025-09-19 | 3.5714
01-2372 | Punch -L2-Pk10-SE | 2025-09-22 | 2025-09-26 | 3.5714
Exterior
Lunch Shelter Upgrades
27-1499 | IP Converge - Lunch Shelter | 2025-08-28 | 2025-09-03 | 5
09-1499 | Exterior Finishes - Lunch Shelter | 2025-09-15 | 2025-09-19 | 3.5714
10-3100 | SS Cable For Bird Netting -Lunch Shelter | 2025-09-15 | 2025-09-19 | 3.5714
10-3101 | Install Bird Netting -Lunch Shelter | 2025-09-17 | 2025-09-23 | 5
05-3110 | Railing - Lunch Shelter | 2025-09-15 | 2025-09-26 | 8.5714
Testing / Sign-offs
HVAC
Start Up/ TAB
32-10505 | IMPACT - NOE - Remobilize / Resume Commissioning | 2025-08-26 | 2025-09-02 | 5.7143
23-9090 | Pre- Functional Checklist -TAB | 2025-05-19 | 2025-09-05 | 78.5714
32-10515 | IMPACT - CCD 091B - Air Distribution to Classrooms | 2025-08-28 | 2025-09-05 | 6.4286
23-9060 | Functional Checklist -TAB | 2025-09-08 | 2025-09-08 | 0.71429
32-10525 | IMPACT - RFC 392.1 - Cannon to Issue CCD-B | 2025-09-08 | 2025-09-12 | 3.5714
23-9100 | TAB Building - TAB | 2025-09-15 | 2025-09-19 | 3.5714
23-9110 | Generate Trend Report | 2025-09-22 | 2025-10-03 | 8.5714
Domestic Water
22-2682 | Fixt Hot Water Test-DWtr | 2025-09-09 | 2025-09-11 | 2.1429
Final Sign-offs & Commissioning
26-9020 | JHA Elect Final | 2025-09-02 | 2025-09-08 | 5
22-9026 | JHA Plum Final | 2025-09-12 | 2025-09-18 | 5
21-2869 | 100 % Building & 10% Site Fire Test | 2025-09-17 | 2025-09-22 | 4.2857
01-7024 | FD Final Signoff / Elevator State Inspection | 2025-09-22 | 2025-09-22 | 0.71429
Gas
22-9285 | Switch Gas from Temp to Main - PKG 10 | 2025-09-02 | 2025-09-08 | 5
Site Work
Finishes
32-3100 | Striping -HomeEc.Pk10,Fin | 2025-09-02 | 2025-09-03 | 1.4286
28-3496 | Exterior Fire Alarm Trim -HomeEc.Pk10,Fin | 2025-09-02 | 2025-09-05 | 2.8571
26-4368 | Exterior Electrical Trim -HomeEc.Pk10,Fin | 2024-11-21 | 2025-09-05 | 206.4286
05-3226 | Guardrail -HomeEc.Pk10,Fin | 2025-09-15 | 2025-09-19 | 3.5714
26-4369 | Set Light Poles on Poured Bases -HomeEc.Pk10,Fin | 2025-09-15 | 2025-09-19 | 3.5714
Utilities
Sewer
33-10159 | IMPACT - LADOT / City Permit Review / BOE Permit | 2025-08-01 | 2025-09-09 | 28.5714
33-3301 | Sewer POC @ Broadway -HomeEc.Pk1-,SS | 2025-09-10 | 2025-09-11 | 1.4286
33-3439 | Backfill Sewer -HomeEc.Pk10,SS | 2025-09-12 | 2025-09-16 | 3.5714
33-3446 | Instl Sewer Drains -HomeEc.Pk1-,SS | 2025-09-12 | 2025-09-18 | 5
Walls / Pads / Misc Concrete
Site Walls
09-5243 | Paint Site Walls -HomeEc.Pk10,StWl | 2025-08-13 | 2025-09-18 | 26.4286
Bio Swale
33-10008 | Install Base & Geotextile Fabric -BioSw-Pk10-StWk | 2025-09-02 | 2025-09-05 | 2.8571
32-9855 | Place Soil -BioSw-Pk10-StWk | 2025-09-08 | 2025-09-09 | 1.4286
05-9280 | Install Grate -BioSw-Pk10-StWk | 2025-09-10 | 2025-09-11 | 1.4286
Ramps
32-10475 | IMPACT - NOE 510 - Waterproofing Exploration - East Ramp | 2025-08-20 | 2025-09-08 | 14.2857
Amphitheater Seating
32-10485 | IMPACT - NOE - Revised Color Selection | 2025-08-06 | 2025-09-02 | 20
32-4436 | Pour Amphitheater Seatings -HomeEc.Pk10,Amp | 2025-09-04 | 2025-09-05 | 1.4286
32-4470 | Cure Amphitheater Seatings -HomeEc.Pk10,Amp | 2025-09-08 | 2025-09-12 | 3.5714
Stairs
32-4439 | Pour Stairs -HomeEc.Pk10,Stair | 2025-09-11 | 2025-09-12 | 1.4286
Hardscape
Flatwork
32-10455 | IMPACT - New Paver Material (CCD __) -HomeEc.Pk10,PCC | 2025-08-19 | 2025-09-02 | 10.7143
32-4452 | Set Pavers -HomeEc.Pk10,PCC | 2025-09-15 | 2025-10-03 | 13.5714
Package 12 (P12) - Admin
P12 - Submittals
Solid State (Led) Lighting - 26 5010
Solid State (Led) Lighting - 26 5010 - Material List
05-10630 | LAUSD Review and Approval - 265010 - Pkg 12 - Material List | 2025-02-07 | 2025-09-01 | 147.8571
Package 13 (P13) - Gym, Bridge
P13 - OLD
Package 13 - Modernize Bridge to East Campus
x26-1399 | Safe Off Area - Electrical -Pk13.Bridge | 2025-09-02 | 2025-09-15 | 10
x02-1390 | Sawcut & Remove Concrete @ Ftg -Pk13.Bridge | 2025-09-16 | 2025-09-22 | 5
x05-1390 | Prep Surface for FRP @ E Pile -Pk13.Bridge | 2025-09-16 | 2025-10-06 | 15
x05-1391 | Install Splay Anchors for FRP @ E Pile -Pk13.Bridge | 2025-09-16 | 2025-10-06 | 15
P13 - Submittals
Concrete Forming Accessories - 031000
03-2913 | Prepare / Submit Shop Dwgs / Submittals - 031000 - Pkg 13 | 2025-05-16 | 2025-09-08 | 82.8571
03-2915 | Procurement - 031000 - Pkg 13 | 2025-09-09 | 2025-09-09 | 0.71429
03-2916 | Delivery - 031000 - Pkg 13 | 2025-09-10 | 2025-09-10 | 0.71429
Cast-In-Place Concrete - 033000
03-70801 | Prepare / Submit Shop Dwgs / Submittals - 033000 - Pkg 13 | 2025-05-16 | 2025-09-08 | 82.8571
03-70811 | LAUSD Review / Approve Shop Dwgs / Submittals - 033000 - Pkg 13 | 2025-09-09 | 2025-09-22 | 10
Structural Steel Framing - 051200
Duct Support Brackets
05-3213 | Prepare / Submit Shop Dwgs / Submittals - 051200 - Pkg 13 (Duct Support Brackets) | 2025-04-17 | 2025-09-08 | 103.5714
05-3233 | LAUSD Review / Approve Shop Dwgs / Submittals - 051200 - Pkg 13 (Duct Support Brackets) | 2025-04-24 | 2025-09-09 | 99.2857
05-3243 | Fabrication - 051200 - Pkg 13 (Duct Support Brackets) | 2025-09-10 | 2025-10-07 | 20
Finish Carpentry - 062000
06-9071 | Prepare / Submit Shop Dwgs / Submittals - 062000 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
06-2596 | LAUSD Review / Approve Shop Dwgs / Submittals - 062000 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Architectural Woodwork - 064000
06-9081 | Prepare / Submit Shop Dwgs / Submittals - 064000 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
06-9091 | LAUSD Review / Approve Shop Dwgs / Submittals - 064000 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Hollow Metal Doors and Frames - 081113
08-9378 | Delivery (readily available when needed)- 081113 - Pkg 13 | 2025-09-02 | 2025-09-08 | 5
Door Hardware - 087100
08-9408 | Delivery (readily available when needed) - 087100 - Pkg 13 | 2025-09-02 | 2025-09-08 | 5
Glazing - 088000
08-4471 | Prepare / Submit Shop Dwgs / Submittals - 088000 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
08-4472 | LAUSD Review / Approve Shop Dwgs / Submittals - 088000 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Non-Structural Metal Framing - 092216
09-9429 | Delivery (readily available when needed) - 092216 - Pkg 13 - Readily Available | 2025-09-02 | 2025-09-08 | 5
Historical Elements Preservation
09-5184 | Prepare / Submit Shop Dwgs / Submittals - Historical Elements - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
09-5185 | LAUSD Review / Approve Shop Dwgs / Submittals - Historical Elements - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Heavy Duty Quartz Vinyl Tile - 096526
09-9509 | Prepare / Submit Shop Dwgs / Submittals - 096526 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
09-9519 | LAUSD Review / Approve Shop Dwgs / Submittals - 096526 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Signage - 101400
10-10083 | Prepare / Submit Shop Dwgs / Submittals - 101400 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
10-10093 | LAUSD Review / Approve Shop Dwgs / Submittals - 101400 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Phenolic Toilet Compartments - 102113
10-10103 | Prepare / Submit Shop Dwgs / Submittals - 102113 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
10-10113 | LAUSD Review / Approve Shop Dwgs / Submittals - 102113 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Cubicle and Shower Curtains - 102123
10-3479 | Prepare / Submit Shop Dwgs / Submittals - 102123 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
10-3480 | LAUSD Review / Approve Shop Dwgs / Submittals - 102123 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Hand and Hair Dryers - 102815
10-10163 | Delivery (Readily Available when needed) - 102815 - Pkg 13 | 2025-09-02 | 2025-09-08 | 5
Metal Lockers - 105113
10-10173 | Prepare / Submit Shop Dwgs / Submittals - 105113 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
10-10183 | LAUSD Review / Approve Shop Dwgs / Submittals - 105113 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Exterior Entrance Floor Mats and Frames - 124815
12-3151 | Prepare / Submit Shop Dwgs / Submittals - 124815 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
12-3152 | LAUSD Review / Approve Shop Dwgs / Submittals - 124815 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Modernize Elevators - 142423
14-2617 | Prepare / Submit Shop Dwgs / Submittals - 142423 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
14-2618 | LAUSD Review / Approve Shop Dwgs / Submittals - 142423 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Fire-Suppression Sprinkler System - 211313
21-3010 | Procurement - 211313 - Pkg 13 | 2025-07-23 | 2025-09-22 | 44.2857
Plumbing - 221000
22-2679 | Procurement - 221000 - Pkg 13 | 2025-06-17 | 2025-09-09 | 60.7143
22-2680 | Delivery - 221000 - Pkg 13 | 2025-09-10 | 2025-09-16 | 5
HVAC Insulation - 230700
23-9929 | Revise / Resubmit Shop Dwgs / Submittals - 230700 - Pkg 13 | 2025-06-27 | 2025-09-22 | 62.8571
Heating, Ventilating and Air Conditioning Equipment - 238000
AAON Air Handler Unit
23-9809 | Air Handler Unit Procurement AAON Unit- 238000 - Pkg 13 | 2025-09-02 | 2025-12-26 | 82.8571
Fan Coil / Condensing Units
23-9369 | Fan Coil / Condensing Units Procurement - 238000 - Pkg 13 | 2025-09-02 | 2025-10-29 | 41.4286
Panelboards and Signal Terminal Cabinets - 262416
26-9974 | Revise and Resubmit Shop Dwgs / Submittals - 262416 - Pkg 13 | 2025-06-19 | 2025-09-15 | 63.5714
26-9984 | LAUSD Review / Approve Shop Dwgs / Submittals - 262416 - Pkg 13 | 2025-09-16 | 2025-10-03 | 12.8571
Solid State (LED) Lighting - 265010
26-10074 | Revise / Resubmit Shop Dwgs / Submittals - 265010 - Pkg 13 | 2025-08-21 | 2025-09-15 | 18.5714
26-9764 | LAUSD Review / Approve Shop Dwgs / Submittals - 265010 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Emergency Generator - 263213
26-4486 | Procurement - 263213 - Pkg 13 | 2025-09-02 | 2025-10-13 | 30
Fire Detection and Alarm - 283100
28-10640 | Revise / Resubmit Shop Dwgs / Submittals - 283100 - Pkg 13 | 2025-06-30 | 2025-09-15 | 55.7143
28-10650 | LAUSD Review / Approve Shop Dwgs / Submittals - 283100 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Carbon Monoxide Detection and Alarm Systems - 283149
28-3480 | Prepare / Submit Shop Dwgs / Submittals - 283149 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
28-3481 | LAUSD Review / Approve Shop Dwgs / Submittals - 283149 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Portable Water Irrigation - 328413
32-10255 | Prepare / Submit Shop Dwgs / Submittals - 328413 - Pkg 13 | 2025-08-01 | 2025-09-12 | 30.7143
32-10265 | LAUSD Review / Approve Shop Dwgs / Submittals - 328413 - Pkg 13 | 2025-09-13 | 2025-09-26 | 10
Irrigation Controls - 328416
32-4399 | Prepare / Submit Shop Dwgs / Submittals - 328416 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
32-4400 | LAUSD Review / Approve Shop Dwgs / Submittals - 328416 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Planting - 329000
32-10266.0 | Prepare / Submit Shop Dwgs / Submittals - 329000 - Pkg 13 | 2025-08-01 | 2025-09-12 | 30.7143
32-10266 | LAUSD Review / Approve Shop Dwgs / Submittals - 329000 - Pkg 13 | 2025-09-13 | 2025-09-26 | 10
Site Water Distribution Systems - 331100
33-10049 | Revise / Resubmit Shop Dwgs / Submittals - 331100 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
33-10059 | LAUSD Review / Approve Shop Dwgs / Submittals - 331100 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Site Sanitary Sewer Utilities - 333000
33-10069 | Prepare / Submit Shop Dwgs / Submittals - 333000 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
33-10079 | LAUSD Review / Approve Shop Dwgs / Submittals - 333000 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Polyvinyl-Chloride Roofing - 075419
08-9608 | Prepare / Submit Shop Dwgs / Submittals - 075419 - Pkg 13 | 2025-02-20 | 2025-09-19 | 151.4286
08-9618 | LAUSD Review / Approve Shop Dwgs / Submittals - 075419 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
Roofing and Deck Insulation - 072200
08-9648 | LAUSD Review / Approve Shop Dwgs / Submittals - 072200 - Pkg 13 | 2025-07-31 | 2025-09-01 | 23.5714
08-9658 | Procurement & Delivery - 072200 - Pkg 13 | 2025-09-02 | 2025-09-29 | 20
Visual Display Units - 101100
10-10094.0 | Prepare / Submit Shop Dwgs / Submittals - 101100 - Pkg 13 | 2025-07-07 | 2025-09-02 | 41.4286
10-10094 | LAUSD Review / Approve Shop Dwgs / Submittals - 101100 - Pkg 13 | 2025-09-03 | 2025-09-16 | 10
10-10094.1 | Procurement - 101100 - Pkg 13 | 2025-09-17 | 2025-10-14 | 20
Formed Metal Wall Panels - 074213.13
07-10175 | Prepare / Submit Shop Dwgs / Submittals - 074213.13 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
07-1010 | Review / Approve Shop Dwgs / Submittals - 074213.13 - Pkg 13 | 2025-09-22 | 2025-10-03 | 8.5714
Flashing and Sheet Metal - 076000
07-10205 | Prepare / Submit Shop Dwgs / Submittals - 076000 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
07-1030 | Review / Approve Shop Dwgs / Submittals - 076000 - Pkg 13 | 2025-09-22 | 2025-10-03 | 8.5714
Painting and Coating - 099000
09-9990 | Review / Approve Shop Dwgs / Submittals - Painting - Pkg 13 | 2025-07-29 | 2025-09-02 | 25.7143
09-10010 | Procurement - Painting - Pkg 13 | 2025-09-03 | 2025-09-30 | 20
Environmental Controls and Energy Management Systems - 230923
23-3010 | Procurement - 230923 - Pkg 13 | 2025-08-25 | 2025-09-02 | 6.4286
23-3011 | Delivery - 230923 - Pkg 13 | 2025-09-03 | 2025-09-03 | 0.71429
Premises Wiring for Convergence of Communication Systems - 271015
27-10691 | Prepare / Submit Shop Dwgs / Submittals - 271015 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
27-2000 | Review / Approve Shop Dwgs / Submittals - 271015 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Clock and Program Systems - 275313
27-10781 | Prepare / Submit Shop Dwgs / Submittals - 275313 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
27-2021 | Review / Approve Shop Dwgs / Submittals - 275313 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
Classroom Sound Enhancement System - 274113
27-10721 | Prepare / Submit Shop Dwgs / Submittals - 274113 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
27-2013 | Review / Approve Shop Dwgs / Submittals - 274113 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
P13 - Construction
Abatement / Demolition
Demolition / Abatement
Roof
C-43 | Demolition - Roof | 2025-06-09 | 2025-09-12 | 68.5714
C-43.1 | IMPACT - Added DSA Scope - Demolition - Roof | 2025-09-15 | 2025-09-19 | 3.5714
Exterior
C-1853.1 | IMPACT - Added DSA Scope - Demolition - Exterior | 2025-09-02 | 2025-09-15 | 10
C-1883 | Abatement - Exterior | 2025-09-16 | 2025-09-22 | 5
Interior Buildout
Level 1
Structural / Concrete / Underslab MEP
C-103.1 | IMPACT - Added DSA Scope - Sawcut Slab - Level 1 | 2025-08-29 | 2025-09-03 | 4.2857
C-113 | Underslab Plumbing - Level 1 | 2025-09-04 | 2025-09-10 | 5
C-113.1 | IMPACT - Added DSA Scope - Underslab Plumbing - Level 1 | 2025-09-11 | 2025-09-17 | 5
C-133 | Patch Concrete Slab on Grade - Level 1 | 2025-09-18 | 2025-09-24 | 5
Roof
C-950 | Plumbing Fixtures / Piping - Roof | 2025-09-22 | 2025-09-26 | 3.5714
C-543 | Install Support Steel - Roof | 2025-09-22 | 2025-10-10 | 13.5714
C-2233 | Screen Wall Supports - Roof | 2025-09-22 | 2025-10-10 | 13.5714
Converged IP Public Address and Intercommunication Systems
27-2019 | PA Device Install | 2025-09-02 | 2025-09-08 | 5
27-2020 | Testing/Commissioning | 2025-09-09 | 2025-09-15 | 5
Exterior
Site
Demo
C-1453 | Construction Fence | 2025-09-02 | 2025-09-03 | 1.4286
C-1233 | Demo Ex. UG Utilities | 2025-09-04 | 2025-09-08 | 3.5714
Grading
C-1083 | Grading / Excavation | 2025-09-09 | 2025-09-10 | 1.4286
C-3653 | IMPACT - Added DSA Scope - Grading / Excavation | 2025-09-11 | 2025-09-12 | 1.4286
C-1093 | Form / Reinforce / Pour - Switchback Ramp Retaining / Cheek Wall Foundations | 2025-09-15 | 2025-09-23 | 6.4286
Hardscape
C-2243.1 | Reinforce - Light Pole Bases - Site | 2025-09-02 | 2025-09-08 | 5
Fire Pump Room (From Package 5)
C-1463 | Fire Riser | 2025-09-04 | 2025-09-10 | 5
C-2283 | Underground Electrical | 2025-09-11 | 2025-09-17 | 5
C-2293 | Underground Plumbing | 2025-09-11 | 2025-09-17 | 5
C-2303 | Equipment Pads | 2025-09-18 | 2025-09-24 | 5
Bridge
C-1723 | Structural Improvements (Dowel / Drill / Epoxy / Rebar) | 2025-08-25 | 2025-09-08 | 10.7143
C-2273 | Form / Pour - Column Strengthening | 2025-09-09 | 2025-09-15 | 5
C-1663 | Patch Concrete | 2025-09-16 | 2025-09-22 | 5
Package 14 (P14) - New Classroom Building w Elevator
P14 - Submittals
Package 14 - Bldg H - New Classroom Building
Submittals
Architectural Woodwork - 064000
06-2119 | Fabrication - 064000 - Pkg 14 | 2025-09-02 | 2025-11-10 | 50
Metal Wall Panels - 074213
Metal Wall Panels - 074213 - Shop Drawings
07-2510 | Fabrication - 074213 - Pkg 14 | 2025-07-11 | 2025-09-18 | 50
07-2511 | Delivery - 074213 - Pkg 14 | 2025-09-19 | 2025-09-19 | 0.71429
Mineral Fiber-Reinforced Cementitious Panels - 074456
07-10125 | Material Lead Time - 074456 - Pkg 14 | 2025-05-30 | 2025-09-08 | 72.8571
07-4103 | Delivery - 074456 - Pkg 14 | 2025-09-09 | 2025-09-09 | 0.71429
Interior Expansion Joint Cover Assemblies - 079513.13
07-10055 | Prepare and Submit to LAUSD - 079513.13 - Pkg 14 | 2025-03-03 | 2025-09-19 | 143.5714
07-4105 | LAUSD Review & App'l - 079513.13 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Exterior Expansion Joint Cover Assemblies - 079513.16
07-9965 | Prepare and Submit to LAUSD - 079513.16 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
07-4109 | LAUSD Review & App'l - 079513.16 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Moisture Testing for Flooring Installation - 090565
09-9589 | Prepare and Submit to LAUSD - 090565 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
Visual Display Units - 101100
10-10263 | Prepare and Submit to LAUSD - 101100 - Pkg 14 | 2025-01-20 | 2025-09-05 | 163.5714
10-2386 | LAUSD Review & App'l - 101100 - Pkg 14 | 2025-01-20 | 2025-09-19 | 173.5714
10-2387 | Fabrication - 101100 - Pkg 14 | 2025-09-22 | 2025-10-17 | 18.5714
Signage - 101400
10-10273 | Prepare and Submit to LAUSD - 101400 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
10-2390 | LAUSD Review & App'l - 101400 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Steel Storage Assemblies - 105613
10-10283 | Prepare and Submit to LAUSD - 105613 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
10-2426 | LAUSD Review & App'l - 105613 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Metal Book Shelving MS & HS Text Book Rooms - 105616
10-10293 | Prepare and Submit to LAUSD - 105616 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
10-2442 | LAUSD Review & App'l - 105616 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Mobile Storage Shelving - 105626
10-2435 | Fabrication - 105626 - Pkg 14 | 2025-05-02 | 2025-09-02 | 88.5714
Roller Window Shades - 122113
12-8042 | Prepare and Submit to LAUSD - 122113 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
Wood Laboratory Casework - 123553
12-3620 | Fabrication - 123553 - Pkg 14 | 2025-09-02 | 2025-11-25 | 60.7143
Bicycle Racks - 129313
12-2503 | Fabrication - 129313 - Pkg 14 | 2025-05-01 | 2025-09-02 | 89.2857
Parking Lot and Site LED Lighting - 265617
26-9914 | Revise and Resubmit - 265617 - Pkg 14 | 2025-01-27 | 2025-09-03 | 157.1429
26-9924 | LAUSD Review & App'l - 265617 - Pkg 14 | 2025-09-04 | 2025-09-23 | 14.2857
Access Control System (ACS) - 281000
28-2671 | Fabrication - 281000 - Pkg 14 | 2024-11-01 | 2025-09-02 | 218.5714
Video Monitoring and Surveillance Systems (CCTC) - 282300
28-2697 | Fabrication - 282300 - Pkg 14 | 2025-09-02 | 2025-09-29 | 20
Carbon Monoxide Detection and Alarm Systems - 283149
28-10750 | Prepare and Submit - 283149 - Pkg 14 | 2023-07-19 | 2025-09-15 | 564.2857
28-2682 | LAUSD Review & App'l - 283149 - Pkg 14 | 2025-09-16 | 2025-09-29 | 10
Chain Link Fences and Gates - 323113
32-P14090 | Prepare and Submit to LAUSD - 323113 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-P14030 | LAUSD Review & App'l - 323113 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Ornamental Fencing and Gates - 323116
32-P14100 | Prepare and Submit to LAUSD - 323116 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-P14050 | LAUSD Review & App'l - 323116 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Architectural Concrete - 323300
32-P14130 | Prepare and Submit to LAUSD - Precast Conc Benches - Pkg 14 | 2025-04-24 | 2025-09-15 | 103.5714
32-P14060 | LAUSD Review & App'l - Precast Conc Benches - Pkg 14 | 2025-09-16 | 2025-09-29 | 10
Portable Water Irrigation - 328413
32-10325 | Prepare and Submit to LAUSD - 328413 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-2758 | LAUSD Review & App'l - 328413 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Irrigation Controls - 328416
32-10335 | Prepare and Submit to LAUSD - 328416 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-2762 | LAUSD Review & App'l - 328416 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
Planting - 329000
32-10345 | Prepare and Submit to LAUSD - 329000 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-2766 | LAUSD Review & App'l - 329000 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
P14 - Construction
Site Work
Utilities
Courtyard
Storm Drain
33-2794 | Install SD Piping -Utl-Pk14-Site | 2025-05-12 | 2025-09-08 | 85.7143
33-2795 | Instl Catch Basins -Utl-Pk14-Site | 2025-05-19 | 2025-09-08 | 80.7143
33-2796 | Instl Divrsn Struct -Utl-Pk14-Site | 2025-05-19 | 2025-09-08 | 80.7143
33-2797 | Instl SD SW Outlts -Utl-Pk14-Site | 2025-05-19 | 2025-09-08 | 80.7143
33-2798 | Test SD -Utl-Pk14-Site | 2025-09-09 | 2025-09-10 | 1.4286
33-2799 | Backfill SD -Utl-Pk14-Site | 2025-09-11 | 2025-09-15 | 3.5714
Fire Water
21-2525 | Exc FW -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
21-2526 | Instl FW Piping -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2527 | FW Thrst Blks -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2528 | Instl FW Bckflw Prvt -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2529 | Instl FW PIV -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2530 | Instl Fire Hydrant -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
Electrical
26-2607 | Exc/Trnch Elect -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2608 | Instl Elect Line -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2609 | Set Pl Boxs -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2610 | Test Elect Lines -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2611 | Backfill Elect -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2612 | Wall Pen/WP -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2613 | Instl Telecm Lines -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2618 | Set Telecm Vaults -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2615 | Electrical Pathways -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2616 | Telecm Pathways -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
Building
Roof
06-9011 | Mechnical Screens -Rf-Pk14-Str | 2025-09-02 | 2025-09-15 | 10
23-P14310 | Envi/Enrg Mgm Sys -Roof-Pk14 | 2025-09-02 | 2025-09-15 | 10
Enclosure
West Elevation
Plaster
09-2671 | Scratch -West-Pk14-Ext | 2025-09-12 | 2025-09-18 | 5
09-2676 | Cure -West-Pk14-Ext | 2025-09-19 | 2025-09-20 | 1.4286
09-2672 | Brown Coat -West-Pk14-Ext | 2025-09-22 | 2025-09-25 | 2.8571
South Elevation
Plaster
09-10050 | IMPACT CCD 28A - DSA Review -South-Pk14-Ext | 2025-07-23 | 2025-09-11 | 36.4286
09-10060 | IMPACT CCD 28A - Late DSA Review -South-Pk14-Ext | 2025-08-06 | 2025-09-11 | 26.4286
09-6669 | Scratch -South-Pk14-Ext | 2025-09-12 | 2025-09-18 | 5
09-6673 | Cure -South-Pk14-Ext | 2025-09-19 | 2025-09-20 | 1.4286
09-6670 | Brown Coat -South-Pk14-Ext | 2025-09-22 | 2025-09-26 | 3.5714
East Elevation
Framing
07-4042 | Exterior Waterproof Openings -East-Pk14-Ext | 2025-09-02 | 2025-09-08 | 5
Plaster
09-6676 | Lath -East-Pk14-Ext | 2025-09-12 | 2025-09-18 | 5
09-6677 | Scratch -East-Pk14-Ext | 2025-09-19 | 2025-09-25 | 5
Interiors
Level 1
Corridor (Exterior)
09-1034 | Drywall Ceilings -L1-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
01-2028 | 2Side Screw Off Insp -L1-Pk14-Int | 2025-09-08 | 2025-09-08 | 0.71429
09-1035 | Tape -L1-Pk14-Int | 2025-09-09 | 2025-09-17 | 6.4286
09-1030 | Prime & 1st Coat Paint -L1-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
Restrooms
09-2735 | Waterproofing -L1-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
Electrical Room
26-1000 | Elect Panels -L1-Pk14-Int | 2025-08-15 | 2025-09-02 | 13.5714
26-1007 | Motor Control Device -L1-Pk14-Int | 2025-09-03 | 2025-09-04 | 1.4286
27-1004 | Set LV Cabs/Eq -L1-Pk14-Int | 2025-09-03 | 2025-09-05 | 2.1429
00-1402 | Set Electrical Equipment | 2025-09-02 | 2025-09-08 | 5
26-1006 | LV Transformer -L1-Pk14-Int | 2025-09-08 | 2025-09-10 | 2.1429
26-1008 | Pull/Terminate Feeders -L1-Pk14-Int | 2025-09-05 | 2025-09-22 | 12.8571
26-1003 | Pull/Term LV Branch -L1-Pk14-Int | 2025-09-11 | 2025-10-01 | 15
IDF Room
27-P14050 | LV Horizontal Copper Rough-in - Level 1 | 2025-09-02 | 2025-09-04 | 2.1429
26-2778 | LV Transformer -L1-Pk14-Int | 2025-09-05 | 2025-09-09 | 3.5714
27-P14070 | LV Term, Label & Test - Level 1 | 2025-09-10 | 2025-09-12 | 2.1429
26-2780 | Pull/Terminate Feeders -L1-Pk14-Int | 2025-09-02 | 2025-09-17 | 11.4286
26-2776 | Pull/Term LV Branch -L1-Pk14-Int | 2025-09-10 | 2025-09-30 | 15
26-2775 | Pull/Term Branch -L1-Pk14-Int | 2025-09-18 | 2025-10-03 | 11.4286
Interior - Ceramics Department
01-2014 | 1Side Screw Off Insp -L1-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
21-2542 | RI FSprink Drops -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
26-2637 | RI Elect Drops -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
23-2612 | RI Mech Drops -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
01-2076 | MEPS Drops Insp -L1-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
07-1001 | Insulate Walls & Clngs -L1-Pk14-Int | 2025-09-11 | 2025-09-17 | 5
27-1003 | CATV Mounting Plates -L1-Pk14-Int | 2025-09-18 | 2025-09-18 | 0.71429
09-2819 | Wall Backing -L1-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
Interior - Flex Engineering / Textbook Storage
01-2121 | MEPS Drops Insp -L1-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3068 | Insulate Walls & Clngs -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3984 | CATV Mounting Plates -L1-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
09-5040 | Wall Backing -L1-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2117 | Ins/Close Wall Insp -L1-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-P14040 | Drywall 2Side -L1-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
Interior - Special Ed
21-2570 | RI FSprink Drops -L1-Pk14-Int | 2025-08-25 | 2025-09-02 | 6.4286
26-4225 | RI Elect Drops -L1-Pk14-Int | 2025-08-25 | 2025-09-02 | 6.4286
23-2886 | RI Mech Drops -L1-Pk14-Int | 2025-08-25 | 2025-09-02 | 6.4286
01-2132 | MEPS Drops Insp -L1-Pk14-Int | 2025-09-03 | 2025-09-03 | 0.71429
07-3069 | Insulate Walls & Clngs -L1-Pk14-Int | 2025-09-04 | 2025-09-10 | 5
27-3986 | CATV Mounting Plates -L1-Pk14-Int | 2025-09-11 | 2025-09-11 | 0.71429
09-5055 | Wall Backing -L1-Pk14-Int | 2025-09-11 | 2025-09-17 | 5
01-2128 | Ins/Close Wall Insp -L1-Pk14-Int | 2025-09-18 | 2025-09-18 | 0.71429
09-5045 | Drywall 2Side -L1-Pk14-Int | 2025-09-19 | 2025-09-25 | 5
Level 2
Corridor (Exterior)
26-4248 | Lighting Control System -L2-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
26-4250 | Clng Light Fixt -L2-Pk14-Int | 2025-08-15 | 2025-09-08 | 17.8571
09-5084 | Final Above Clng Insp -L2-Pk14-Int | 2025-09-09 | 2025-09-09 | 0.71429
01-2149 | MEPS RI Insp -L2-Pk14-Int | 2025-09-09 | 2025-09-09 | 0.71429
09-5075 | Waterproofing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
07-3072 | Insulate Clngs -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
Restrooms
09-5098 | Waterproofing -L2-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
Electrical Room
26-4226 | Elect Panels -L2-Pk14-Int | 2025-08-18 | 2025-09-02 | 11.4286
26-4231 | Motor Control Device -L2-Pk14-Int | 2025-09-03 | 2025-09-04 | 1.4286
27-3987 | Set LV Cabs/Eq -L2-Pk14-Int | 2025-09-03 | 2025-09-05 | 2.1429
26-4230 | LV Transformer -L2-Pk14-Int | 2025-09-08 | 2025-09-10 | 2.1429
26-4232 | Pull/Terminate Feeders -L2-Pk14-Int | 2025-09-05 | 2025-09-22 | 12.8571
26-4228 | Pull/Term LV Branch -L2-Pk14-Int | 2025-09-11 | 2025-10-01 | 15
IDF Room
26-4260 | Elect Panels -L2-Pk14-Int | 2025-08-18 | 2025-09-02 | 11.4286
27-P14060 | LV Horizontal Copper Rough-in - Level 2 | 2025-09-02 | 2025-09-04 | 2.1429
26-4264 | LV Transformer -L2-Pk14-Int | 2025-09-03 | 2025-09-05 | 2.1429
27-P14040 | LV Copper/Fiber Backbone Terminations & Testing | 2025-09-05 | 2025-09-09 | 3.5714
27-P14080 | LV Term, Label & Test - Level 2 | 2025-09-10 | 2025-09-12 | 2.1429
26-4266 | Pull/Terminate Feeders -L2-Pk14-Int | 2025-09-03 | 2025-09-18 | 11.4286
26-4262 | Pull/Term LV Branch -L2-Pk14-Int | 2025-09-08 | 2025-09-26 | 13.5714
26-4261 | Pull/Term Branch -L2-Pk14-Int | 2025-09-19 | 2025-10-06 | 12.8571
Interior - Art Department
01-2157 | MEPS Drops Insp -L2-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3070 | Insulate Walls & Clngs -L2-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3990 | CATV Mounting Plates -L2-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
09-5109 | Wall Backing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2139 | Ins/Close Wall Insp -L2-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-5061 | Drywall 2Side -L2-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
Interior - Chemistry
01-2175 | MEPS Drops Insp -L2-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3073 | Insulate Walls & Clngs -L2-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3995 | CATV Mounting Plates -L2-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
09-5125 | Wall Backing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2171 | Ins/Close Wall Insp -L2-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-5115 | Drywall 2Side -L2-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
Interior - Gen Classroom
01-2186 | MEPS Drops Insp -L2-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3074 | Insulate Walls & Clngs -L2-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3997 | CATV Mounting Plates -L2-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
27-P14250 | AV Cabling - L2 | 2025-09-10 | 2025-09-12 | 2.1429
09-5140 | Wall Backing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2182 | Ins/Close Wall Insp -L2-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-5130 | Drywall 2Side -L2-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
Testing / Sign-offs
New Classroom Permanent Power for Elevator
00-1403 | Wiring for Main Electric Equipment / Bollards | 2025-09-09 | 2025-09-22 | 10
Electrical Start-up
Permanent Power
26-2001 | Complete House & E Pwr Risers-PPwr | 2025-09-02 | 2025-09-02 | 0.71429
Elevator
Elevator Machine Room
09-1021 | Tape -L1-Pk14-Int | 2025-08-14 | 2025-09-08 | 18.5714
09-1016 | Sealed Conc Floors -L1-Pk14-Int | 2025-09-09 | 2025-09-11 | 2.1429
Package 15 (P15) - New M&O, Solar, Parking Lot, Horticulture
P15 - Construction
New
Hardscape & Landscaping
Parking Lots
A102400 | Remove Interim Housing - Below Grade - West (Phase 6) | 2025-09-01 | 2025-09-10 | 7.1429
A102410 | Subgrade Prep | 2025-09-11 | 2025-09-15 | 3.5714
Package 16 (P16) - Non-DSA Betterment Package
P16 - Construction
Federal Building
Summer 2025
09-P160030 | Paint (e) Casework - Federal Bldg - Level 1 | 2025-09-02 | 2025-09-08 | 5
09-P160040 | Paint (e) Casework - Federal Bldg - Level 2 | 2025-09-09 | 2025-09-15 | 5
12-P160050 | Install (n) Window Blinds - Federal Bldg - Level 1 | 2025-09-09 | 2025-09-15 | 5
09-P160070 | Paint (e) Metal Lockers - Federal Bldg - Level 1 | 2025-09-09 | 2025-09-15 | 5
12-P160060 | Install (n) Window Blinds - Federal Bldg - Level 2 | 2025-09-16 | 2025-09-22 | 5
09-P160080 | Paint (e) Metal Lockers Federal Bldg - Level 2 | 2025-09-16 | 2025-09-22 | 5
09-P160090 | Paint Exterior Wall - Federal Building | 2025-09-09 | 2025-09-29 | 15
Music Building
Summer 2025
09-P160110 | Paint (e) Casework - Music Building | 2025-09-02 | 2025-09-08 | 5
Auditorium
Summer 2025
09-P160180 | Paint Exterior Wall - North - Auditorium | 2025-09-02 | 2025-09-08 | 5
09-P160190 | Paint Exterior Wall - South - Auditorium | 2025-09-09 | 2025-09-22 | 10
Phase 6 Final Construction
New Batting Cages
02-5050 | Site Demo -Pk2.NFH (Batting Cage Pending) | 2023-09-05 | 2025-09-03 | 521.4286
02-2880 | Clear & Grub Site -Pk2.NFH (Batting Cage Pending) | 2023-08-28 | 2025-09-04 | 527.8571
[5 empty] | Lincoln High School - LIVE FILE - TRUE LIVE FILE | [14 empty] | © 2025 XER2XLSXGANTT

## 6 Week Look Ahead (D
[5 empty] | 6 Week Look Ahead (D | [24 empty] | Data Date : 09/01/2025
Activity ID | Activity Name | Start | Finish | Duration (Workdays) | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13
Lincoln High School - LIVE FILE - TRUE LIVE FILE
Overall Project
Milestones
MS14 - Commissioning
MS14.3.10 | Full Commissioning Reports / PSR - Phase 3 - Home Ec Bldg | 2025-07-09 | 2025-09-29 | 59.2857
MS14.3.07 | Full Commissioning Reports / PSR - Phase 3 - New Perf Arts Annx | 2025-07-18 | 2025-10-10 | 60.7143
MS14.4.06 | Full Commissioning Reports / PSR - Phase 4 - Interim Housing B | 2025-10-07 | 2025-12-05 | 42.8571
MS15 - Beneficial Occupancies
10-10033 | Auditorium Occupancy Phase 2 Summer 2025 | 2025-09-02 | 2025-09-02 | 0.71429
MS15.3.23 | Beneficial Occupancy - Phase 3 - Ramps & Historic Stairs | 2025-09-30 | 2025-09-30 | 0.71429
Pinner Costs
Allowances
AD-03 | ADA-03 - ACCM Asphalt Abatement & Removal | 2023-06-01 | 2025-09-01 | 588.5714
T-508 | Pkg 5 Track & Field, Added Design & Constr. Fees | 2023-06-26 | 2025-09-01 | 570.7143
T-642 | Pkg 2 CD 73 Furnish DW & SS at N concession stand | 2025-02-25 | 2025-09-01 | 135
T-528 | DD 018 Lighting Control nLights - Construction Costs | 2024-06-01 | 2025-09-02 | 327.8571
T-677 | De-scope of Countertop and Removal of Pre-Installed Attachment Brackets | 2025-03-31 | 2025-09-03 | 112.1429
T-621 | Pkg5 DBD29 Scoreboard Relocation Construction Fees | 2025-09-01 | 2025-09-05 | 3.5714
T-662 | Install Outdoor Horticultural Sink (Design | 2025-09-01 | 2025-09-05 | 3.5714
T-663 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-664 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-665 | Provide Electronic Door Lockset at B-217 | 2025-09-01 | 2025-09-05 | 3.5714
T-666 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-667 | Countertop Descope | 2025-09-01 | 2025-09-05 | 3.5714
T-669 | Additional Abatement at Administration Building | 2025-09-01 | 2025-09-05 | 3.5714
T-670 | Additional Abatement at Gymnasium Building | 2025-09-01 | 2025-09-05 | 3.5714
T-671 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-675 | Pkg 1 CD127 Remove RAW at B-33 | 2025-09-01 | 2025-09-05 | 3.5714
T-678 | Washer Dryer and Utility Sink | 2025-09-01 | 2025-09-05 | 3.5714
T-679 | VOID(T-681) | 2025-09-01 | 2025-09-05 | 3.5714
T-680 | Update Graphic Package | 2025-09-01 | 2025-09-05 | 3.5714
T-681 | Geo-Textile Fabric_Home Ec_ | 2025-09-01 | 2025-09-05 | 3.5714
T-682 | Existing Storage Container Relocation PKG 5 | 2025-09-01 | 2025-09-05 | 3.5714
T-683 | Pkg 9 CD128 Duct Leakage Repair | 2025-09-01 | 2025-09-05 | 3.5714
T-684 | Basement Door Changes | 2025-09-01 | 2025-09-05 | 3.5714
T-685 | Replace Current Chain Link by HOMEC Building | 2025-09-01 | 2025-09-05 | 3.5714
T-686 | Remove Video Dome Camera from Elev. Cab | 2025-09-01 | 2025-09-05 | 3.5714
T-687 | Provide and Install 1 New Storage Container | 2025-09-01 | 2025-09-05 | 3.5714
T-688 | Relocate Player Benches from East Plateau | 2025-09-01 | 2025-09-05 | 3.5714
T-690 | A/E Services for Change in Refrigerant for PKG 13 | 2025-09-01 | 2025-09-05 | 3.5714
T-692 | A/E Service for New Picket Fence on Package 7 | 2025-09-01 | 2025-09-05 | 3.5714
T-694 | Addt'l Fencing and Gates | 2025-09-01 | 2025-09-05 | 3.5714
T-691 | TBD | 2025-09-01 | 2025-09-05 | 3.5714
T-695 | PKG 9 Repair Audit. (E) HVAC duct damages | 2025-09-01 | 2025-09-05 | 3.5714
T-697 | PKG 7, 14 DBD24 Curtain Wall WAter/Air Testing | 2025-09-01 | 2025-09-05 | 3.5714
T-698 | ADA Card Service | 2025-09-01 | 2025-09-05 | 3.5714
T-700 | Dispose Pavers, Concrete Benches | 2025-09-01 | 2025-09-05 | 3.5714
T-693 | Additional Security Screen | 2025-09-01 | 2025-09-05 | 3.5714
T-646 | PKG 14 P14-RFC 34-D_Wiring Projectors and AVEquipment | 2025-02-24 | 2025-09-25 | 152.8571
T-647 | TBD | 2025-02-24 | 2025-09-25 | 152.8571
T-648 | PKG 6 CD 108_Utility Sink at Int.Lockers-Design Fee | 2025-02-24 | 2025-09-25 | 152.8571
T-649 | PKG 7 CD 112 Dbl swing gates w hinges at NPA n. entry ramp | 2025-02-24 | 2025-09-25 | 152.8571
T-650 | PKG 6 CD 95 Boys Locker Room Washer and Dryer utility -Design Only | 2025-02-24 | 2025-09-25 | 152.8571
T-652 | Connect Intrusion System to Sitewide Network | 2025-02-24 | 2025-09-25 | 152.8571
T-653 | Auditorium clean up | 2025-02-24 | 2025-09-25 | 152.8571
T-654 | Spec Updates for discontinued Light Fix | 2025-02-24 | 2025-09-25 | 152.8571
T-655 | Provide Metal Screen and Guardrail at Ramp 1 | 2025-02-24 | 2025-09-25 | 152.8571
T-656 | Paint auditorium foyer ceiling | 2025-02-24 | 2025-09-25 | 152.8571
T-657 | Interim Weight Room and Canopies | 2025-02-24 | 2025-09-25 | 152.8571
T-658 | Theatrical Pipe Rigging(Design Only) | 2025-02-24 | 2025-09-25 | 152.8571
Construction Schedule
CS-1002 | COST-CPM Schedule Monthly Update (Construction) - Package 1 | 2022-06-13 | 2025-09-02 | 841.4286
CS-1005 | Approved CPM Schedule - Package 14 | 2023-06-01 | 2025-09-03 | 590
Environmental Import/Export Material Testing
ET-1001 | COST-Environmental Soils Testing - Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
Overhead, Construction Facilities & Temp. Controls
Package 1
PH1-101 | COST-Insurance - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-102 | COST-DB Project Manager - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-103 | COST-Project Manager - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-104 | COST-General Superintendent - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-105 | COST-Safety Manager - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-106 | COST-Additional Project Staff - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-107 | COST-Quality Control - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-108 | COST-BIM - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-109 | COST-Site Temp Fencing - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-112 | COST-Vehicle/Fuel - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-113 | COST-Field Office Rental - IOR (Monthly) - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-114 | COST-Field Office Rental - LAUSD/PEX (Monthly) - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-115 | COST-Field Office Rental - Pinner (Monthly) - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-116 | COST-Home Office - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-117 | COST-Permits - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-118 | COST-Temporary Electric - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-119 | COST-Temporary Water - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-120 | COST-Temporary Toilets - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-121 | COST-Traffic Control - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-122 | COST-Security - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-123 | COST-Interim Cleanup - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-124 | COST-Final Cleanup - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-125 | COST-Equipment Repair/Small Tools/Tool Shed/Safety - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-126 | COST-Dust Control - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-127 | COST-Project Record Documents/As-Builts - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-129 | COST-Dumpsters - Pkg1 | 2022-06-13 | 2025-09-02 | 841.4286
PH1-128 | COST-Closeout Documents - Pkg1 | 2022-06-13 | 2025-09-24 | 857.1429
Package 4
PH4-201 | COST-Insurance - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-202 | COST-DB Project Manager - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-203 | COST-Project Manager - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-204 | COST-General Superintendent - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-205 | COST-Safety Manager - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-206 | COST-Additional Project Staff - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-207 | COST-Quality Control - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-208 | COST-BIM - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-209 | COST-Site Temp Fencing - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-210 | COST-Office Furniture & Equipment/Supplies - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-211 | COST-Vehicle/Fuel - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-212 | COST-Field Office Rental - IOR (Monthly) - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-213 | COST-Field Office Rental - LAUSD/PEX (Monthly) - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-214 | COST-Field Office Rental - Pinner (Monthly) - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-215 | COST-Home Office - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-216 | COST-Permits - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-217 | COST-Temporary Electric - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-218 | COST-Temporary Water - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-219 | COST-Temporary Toilets - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-220 | COST-Traffic Control - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-221 | COST-Security - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-222 | COST-Interim Cleanup - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-223 | COST-Final Cleanup - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-224 | COST-Equipment Repair/Small Tools/Tool Shed/Safety - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-225 | COST-Dust Control - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-226 | COST-Project Record Documents/As-Builts - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-227 | COST-Closeout Documents - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
PH4-228 | COST-Dumpsters - Pkg4 | 2023-03-06 | 2025-09-06 | 654.2857
Package 6
13-P6010 | Monthly Rental - Interim Housing - West Campus | 2025-09-03 | 2027-04-21 | 425.7143
23-P6010 | Monthly Interim Housing Air Filter Replacement | 2025-09-03 | 2027-04-21 | 425.7143
General Conditions
GC-1003 | COST-Package 1: Fee | 2022-06-13 | 2025-09-03 | 842.1429
GC-1012 | 4-4: Historic Stair Replacement - Package 5: CA Services - Alternates | 2023-07-18 | 2025-09-03 | 556.4286
GC-1004 | COST-Package 4: Fee | 2023-03-06 | 2025-09-06 | 654.2857
GC-1008 | COST-4-2: Teacher Shuttle - Package 4 - Alternates | 2023-03-06 | 2025-09-06 | 654.2857
Field Engineering
FE-1002 | COST-Field Engineering/Survey - Package 4 | 2023-03-06 | 2025-09-05 | 653.5714
SWPPP
PH1-130 | COST-Implement SWPPP - Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
PH1-131 | COST-SWPPP Maintenance - Duration of Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
PH4-229 | COST-Implement SWPPP - Package 4 | 2023-03-06 | 2025-09-05 | 653.5714
PH4-230 | COST-SWPPP Maintenance - Duration of Package 4 | 2023-03-06 | 2025-09-05 | 653.5714
Contract Closeout
PH1-132 | COST-Punchlist - Package 1 | 2022-06-13 | 2025-09-03 | 842.1429
PH4-231 | COST-Punchlist - Package 4 | 2023-07-18 | 2025-09-05 | 557.8571
Package 2 (P2) - Field House, DWP, Batting Cages
P2 - Construction
Package 2 - Construct New FieldHouse
Site Work
Utilities
Underground Infrastructure
33-9424 | Wire Pulled -Pk2.NFH.Elec - 800 Bldg to DWP Yard - NS | 2024-01-02 | 2025-09-02 | 435.7143
33-9968 | Inspections -Pk2.NFH.Elec - 800 Bldg to DWP Yard | 2024-07-23 | 2025-09-02 | 290.7143
Package 5 (P5) - East Campus Ramps, Historical Stairs, Elevator Tower
P5 - Construction
Package 5 - Historical Stair - Alternate 4
Electrical
26-5502 | Set Poles -Pk5-HistStr-Elec | 2025-09-02 | 2025-09-09 | 5.7143
26-5503 | Pull Wire -Pk5-HistStr-Elec | 2025-09-10 | 2025-09-16 | 5
26-5504 | Terminate Light Poles -Pk5-HistStr-Elec | 2025-09-10 | 2025-09-16 | 5
Final Sign-offs
26-9475 | JHA Elect Final -Pk5-HistStr | 2025-09-17 | 2025-09-30 | 10
01-9009 | Final Signoffs -Pk5-HistStr | 2025-09-17 | 2025-09-30 | 10
Package 6 (P6) - Interim Housing 1-B, Locker Room, Admin
P6 - Construction
Interim Housing B - West Campus
13-3742 | Set Portables - West Campus (Installation over 3 Saturdays) | 2025-08-26 | 2025-09-02 | 5.7143
22-9125 | Install DCW Shut-Off Valve, Cleanout & Yard Box - West Campus | 2024-12-18 | 2025-09-02 | 185
32-10225 | AC Overlay Ramp Toe - West Campus | 2025-09-03 | 2025-09-04 | 1.4286
13-3752 | Set Handrails - West Campus | 2025-09-05 | 2025-09-08 | 2.8571
26-9594 | Final Electrical Connections to Units - West Campus | 2025-09-03 | 2025-09-09 | 5
27-10521 | LV Mobilization - West Campus | 2025-09-10 | 2025-09-10 | 0.71429
10-10073 | Signage - West Campus | 2025-09-09 | 2025-09-11 | 2.1429
22-9145 | Install Drinking Fountains - West Campus | 2025-09-09 | 2025-09-11 | 2.1429
22-9135 | Install Condensate & Connect to Existing Utility - West Campus | 2025-09-10 | 2025-09-12 | 2.1429
05-9390 | DF Rails - West Campus | 2025-09-12 | 2025-09-15 | 2.8571
28-10600 | Fire Alarm Trim - West Campus | 2025-09-09 | 2025-09-15 | 5
27-10471 | Converged IP Device Install - West Campus | 2025-09-09 | 2025-09-15 | 5
27-10481 | AV Cabling - West Campus | 2025-09-09 | 2025-09-15 | 5
28-10610 | Security Cable Rough-in - West Campus | 2025-09-09 | 2025-09-15 | 5
22-9155 | Connect DW & SS to Units - West Campus | 2025-09-10 | 2025-09-16 | 5
32-10235 | Set / Install Fence - West Campus | 2025-09-10 | 2025-09-16 | 5
26-9584 | Set Mounted Lights - West Campus | 2025-09-10 | 2025-09-16 | 5
27-10531 | LV Horizontal Copper Rough-in - West Campus | 2025-09-10 | 2025-09-16 | 5
27-P6040 | LV Copper/Fiber Backbone Terminations & Testing - West Campus | 2025-09-10 | 2025-09-16 | 5
26-9604 | Run Elec Conduit to Ext Lts & Terminate - West Campus | 2025-09-10 | 2025-09-18 | 6.4286
12-8022 | Window Blinds - West Campus | 2025-09-16 | 2025-09-22 | 5
28-10620 | Security Device Install - West Campus | 2025-09-16 | 2025-09-22 | 5
27-10491 | Converged IP Testing/Commissioning - West Campus | 2025-09-16 | 2025-09-22 | 5
27-10501 | AV Trim and Device Install - West Campus | 2025-09-16 | 2025-09-22 | 5
32-10245 | Set Gates - West Campus | 2025-09-17 | 2025-09-23 | 5
27-10511 | AV Headend Install - West Campus | 2025-09-23 | 2025-09-29 | 5
27-10541 | LV IDF/LDF Buildout - West Campus | 2025-09-16 | 2025-09-29 | 10
13-3762 | Set FF&E - West Campus | 2025-09-17 | 2025-09-30 | 10
10-P6010 | Toilet Accessories - West Campus | 2025-09-17 | 2025-09-30 | 10
27-10551 | AV Testing/Commissioning - West Campus | 2025-09-30 | 2025-10-06 | 5
27-10561 | LV Term, Label & Test - West Campus | 2025-09-30 | 2025-10-06 | 5
27-P6050 | OFCI Equipment Install - West Campus | 2025-09-30 | 2025-10-06 | 5
27-P6060 | Clock Install - West Campus | 2025-09-30 | 2025-10-06 | 5
27-P6070 | PA Device Install - West Campus | 2025-09-30 | 2025-10-06 | 5
00-8898 | Punch - West Campus | 2025-10-01 | 2025-10-07 | 5
27-P6080 | Testing/Commissioning - West Campus | 2025-10-07 | 2025-10-27 | 15
28-P6020 | Closeout Documentation - 280120 | 2025-10-07 | 2025-10-27 | 15
28-P6030 | Programming and Commissioning - West Campus | 2025-10-07 | 2025-10-27 | 15
00-8908 | Final Sign-offs - West Campus | 2025-10-08 | 2025-10-28 | 15
Install Interim Locker Rooms at Tennis Courts
East Campus - Locker Room Portables
12-P6010 | Window Blinds - West Campus | 2025-09-02 | 2025-09-08 | 5
Package 7 (P7) - Performing Arts
P7 - Submittals
Package 7 - Bldg J -Perf. Arts
Submittals
Roller Window Shades - 122413
12-8082 | Fabricate - 122413 - Pkg 7 | 2025-06-20 | 2025-09-04 | 55
Planting - 329000
32-4527 | Prepare and Submit to LAUSD - 329000 - Pkg 7 | 2024-01-02 | 2025-09-02 | 435.7143
32-4528 | LAUSD Review & App'l - 329000 - Pkg 7 | 2025-09-03 | 2025-09-16 | 10
32-10385 | Fabricate - 329000 - Pkg 7 | 2025-09-17 | 2025-10-13 | 19.2857
P7 - Construction
Package 7 - Construct New Performing Arts Building
Roof
01-2469 | Punch -Pk7-Rf | 2025-09-02 | 2025-09-15 | 10
Interiors
Basement
Corridor
01-9115 | Modified Tecum Panel Finishes-LBCorr-Pk7-Int | 2025-09-02 | 2025-09-12 | 7.8571
01-2389 | Final Clean Up -LBCorr-Pk7-Int | 2025-09-15 | 2025-09-17 | 2.1429
01-2470 | Punch -LBCorr-Pk7-Int | 2025-09-15 | 2025-09-17 | 2.1429
IDF Room
27-7018 | Testing/Commissioning | 2025-08-28 | 2025-09-22 | 18.5714
27-7020 | Testing/Commissioning | 2025-08-28 | 2025-09-22 | 18.5714
27-7013 | Final Sign-offs & Commissioning | 2025-09-23 | 2025-09-29 | 5
27-7014 | Closeout Documentation | 2025-09-30 | 2025-10-06 | 5
27-7022 | Closeout Documentation | 2025-09-30 | 2025-10-06 | 5
Interior - Flex Drama / Storage
01-2471 | Punch -FlexD-Pk7-Int | 2025-09-02 | 2025-09-04 | 2.1429
Interior - Computer Lab
01-2489 | Final Clean Up -Comp-Pk7-Int | 2025-09-15 | 2025-09-17 | 2.1429
01-2495 | Punch -Comp-Pk7-Int | 2025-09-18 | 2025-09-22 | 3.5714
01-2499 | FF&E -Comp-Pk7-Int | 2025-09-23 | 2025-09-25 | 2.1429
Elevator Machine Room
01-2383 | Final Clean Up -EMR-Pk7-Int | 2025-09-15 | 2025-09-15 | 0.71429
Elevator
14-2672 | Schedule Elevator Inspector -Elev-Pk7-Int | 2025-09-16 | 2025-09-18 | 2.1429
14-2673 | Elevator Inspection -Elev-Pk7-Int | 2025-09-19 | 2025-09-19 | 0.71429
01-2468 | Punch -Elev-Pk7-Int | 2025-09-22 | 2025-09-24 | 2.1429
Level 1
Corridor
09-5555 | Final Paint -L1Corr-Pk7-Int | 2025-09-02 | 2025-09-04 | 2.1429
10-3665 | Fire Ext & Cabs -L1Corr-Pk7-Int | 2025-09-02 | 2025-09-04 | 2.1429
10-3700 | Janitor Closet Mop Racks -L1-Pk7-Int | 2025-09-05 | 2025-09-05 | 0.71429
10-3667 | Corner Guards -L1Corr-Pk7-Int | 2025-09-05 | 2025-09-09 | 3.5714
01-2523 | Final Clean Up -L1Corr-Pk7-Int | 2025-09-10 | 2025-09-12 | 2.1429
01-2530 | Punch -L1Corr-Pk7-Int | 2025-09-10 | 2025-09-12 | 2.1429
Restrooms
10-3669 | Toilet Accs -Pk7.L1.RR | 2025-09-02 | 2025-09-04 | 2.1429
09-5576 | Final Paint -Pk7.L1.RR | 2025-08-27 | 2025-09-05 | 7.1429
01-2535 | Final Clean Up -Pk7.L1.RR | 2025-09-05 | 2025-09-09 | 3.5714
26-4853 | Intrusion Devices -Pk7.L1.RR | 2025-09-05 | 2025-09-09 | 3.5714
01-2541 | Punch -Pk7.L1.RR | 2025-09-10 | 2025-09-12 | 2.1429
Interior - Media CR / Storage
09-5536 | Final Paint -Pk7.L1.Media | 2025-09-05 | 2025-09-09 | 3.5714
12-3231 | Roller Shades -Pk7.L1.Media | 2025-09-10 | 2025-09-12 | 2.1429
01-2542 | FF&E -Pk7.L1.Media | 2025-09-10 | 2025-09-12 | 2.1429
01-2511 | Final Clean Up -Pk7.L1.Media | 2025-09-15 | 2025-09-17 | 2.1429
11-7003 | Install Divider Curtain -Pk7.L1.Media | 2025-09-15 | 2025-09-19 | 3.5714
01-2531 | Punch -Pk7.L1.Media | 2025-09-22 | 2025-09-24 | 2.1429
Exterior
North Elevation
Framing
07-3258 | Seismic Joints -Pk7.North.Framing | 2025-03-20 | 2025-09-03 | 120
Site Work
Walls / Pads / Misc Concrete
Ramp - North
05-7777 | Install Guardrail -Ramp-Pk7-StWk | 2025-09-16 | 2025-09-22 | 5
Fence / Gate
32-4554 | Dig Fence/Gate Holes -Pk7-StFin - Pending CCD | 2025-08-18 | 2025-09-12 | 18.5714
32-4555 | Set Fence/Gate Posts -Pk7-StFin | 2025-08-20 | 2025-09-19 | 22.1429
32-4556 | Pour Fence/Gate Ftgs -Pk7-StFin | 2025-08-22 | 2025-09-19 | 20.7143
Landscape
32-4577 | Irrigation -Pk7-LS | 2025-08-18 | 2025-09-26 | 28.5714
Canopy
32-7061 | Set Canopy Steel | 2025-09-11 | 2025-09-11 | 0.71429
32-7071 | Weld Conopy Steel | 2025-09-12 | 2025-09-17 | 4.2857
07-7121 | Install Canopy Decking | 2025-09-18 | 2025-09-22 | 3.5714
07-7141 | Metal Framing | 2025-09-23 | 2025-09-25 | 2.1429
07-7131 | Install Rigid Insulation | 2025-09-26 | 2025-09-26 | 0.71429
07-7100 | Install Canopy Gutters -Canopy-Pk7-StWk | 2025-09-29 | 2025-09-30 | 1.4286
07-7103 | Install Flashings & Downspouts -Canopy-Pk7-StWk | 2025-09-29 | 2025-09-30 | 1.4286
07-7104 | Install Canopy Fascia & Signage -Canopy-Pk7-StWk | 2025-09-29 | 2025-09-30 | 1.4286
Finishes
27-4174 | Exterior Low Voltage Trim Pk7-SiteFin | 2025-08-27 | 2025-09-03 | 5.7143
28-3551 | Exterior Fire Alarm Trim Pk7-SiteFin | 2025-08-27 | 2025-09-03 | 5.7143
05-3292 | Guardrail Pk7-SiteFin | 2025-09-23 | 2025-09-25 | 2.1429
32-4580 | Set Gate Pk7-SiteFin | 2025-09-22 | 2025-09-26 | 3.5714
32-4599 | Install Fencing Pk7-SiteFin | 2025-09-22 | 2025-09-26 | 3.5714
05-3291 | Handrails Pk7-SiteFin | 2025-09-26 | 2025-09-30 | 3.5714
26-4666 | Exterior Electrical Trim Pk7-SiteFin | 2025-09-26 | 2025-10-02 | 5
Testing / Sign-offs
Fire Alarm & Fire Sprinkler
28-3543 | NFPA 13 & 24 Testing-FA | 2025-09-04 | 2025-09-15 | 8.5714
28-3545 | NFPA 72 Testing-FA | 2025-09-16 | 2025-09-19 | 2.8571
Domestic Water
22-2795 | Bleed/Flush/Sanitize Risers-DWtr | 2025-09-02 | 2025-09-08 | 5
22-2794 | Hook up Fixt-DWtr | 2025-02-28 | 2025-09-11 | 140
22-2793 | Flush & Chlorination Test-DWtr | 2025-09-12 | 2025-09-18 | 5
22-7999 | Lead Test-DWtr | 2025-09-19 | 2025-09-25 | 5
Final Sign-offs & Commissioning
26-4663 | JHA Elect Final -Pk7-Final | 2025-09-02 | 2025-09-08 | 5
01-7002 | Develop Asset Workbook (MAC Addresses) -Pk7-Final | 2025-09-02 | 2025-09-08 | 5
01-7003 | FTPMG Programming -Pk7-Final | 2025-09-09 | 2025-09-10 | 1.4286
01-2396 | FD Final Signoff -Pk7-Final | 2025-09-19 | 2025-09-19 | 0.71429
22-2798 | JHA Plum Final -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
01-7004 | Commissioning -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
28-8003 | Programming and Commissioning -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
28-8004 | Closeout Documentation -Pk7-Final | 2025-09-19 | 2025-09-25 | 5
01-7777 | Commissioning Report Review/App'l -Pk7-Final | 2025-09-26 | 2025-10-02 | 5
01-7999 | Punchlist Corrections -Pk7-Final | 2025-09-23 | 2025-10-06 | 10
01-2395 | OEHS Pre- Walk -Pk7-Final | 2025-10-07 | 2025-10-07 | 0.71429
01-7700 | OEHS Final Walk -Pk7-Final | 2025-10-08 | 2025-10-13 | 4.2857
01-7000 | 100% PSR & OEHS Occ. Sign-Off -Pk7-Final | 2025-10-08 | 2025-10-14 | 5
Package 8 (P8) - Music, Federal Building Barrier Removal
P8 - Construction
Package 8 - Auditorium Barrier Removal
Finishes Phase 2 (Summer 2025)
28-8027 | Closeout Documentation | 2025-09-02 | 2025-09-15 | 10
27-8010 | Closeout Documentation | 2025-07-09 | 2025-09-17 | 50.7143
Package 8 - Partial Modernize Federal Building
12-8002 | Install (N) Window Coveing-Pk8-Federal | 2025-09-02 | 2025-09-03 | 1.4286
05-8001 | Cane Detectable Rails -Pk8-Federal | 2025-09-02 | 2025-09-03 | 1.4286
01-8004 | Walk/ Acceptance/ADA -Pk8-Federal | 2025-09-04 | 2025-09-08 | 3.5714
28-8024 | Closeout Documentation | 2025-09-02 | 2025-09-08 | 5
Package 8 - Partial Modernize Music Building
01-8001 | Final Commissioning / Pre Functional Testing -Pk8-Music | 2025-09-02 | 2025-09-02 | 0.71429
01-8002 | Walk/ Acceptance/ADA -Pk8-Music | 2025-09-02 | 2025-09-02 | 0.71429
28-10630 | Closeout Documentation | 2025-09-02 | 2025-09-03 | 1.4286
Package 9 (P9) - Mini Plant HVAC
P9 - Construction
Package 9 - Mini Plant HVAC
Exterior
Mech Yard Upgrades
01-9001 | Punch -Yard-Pk9-Ext | 2025-09-08 | 2025-09-12 | 3.5714
Testing / Sign-offs
HVAC
Start Up/ TAB
23-9232 | TAB Review -TAB | 2025-08-07 | 2025-09-09 | 24.2857
23-9236 | Commission Complete -TAB | 2025-09-12 | 2025-09-12 | 0.71429
Final Sign-offs & Commissioning
22-9077 | JHA Plum Final -Pk9.Final | 2025-09-02 | 2025-09-08 | 5
26-9473 | JHA Elect Final -Pk9.Final | 2025-09-02 | 2025-09-08 | 5
23-9239 | Generate Trend Report | 2025-08-28 | 2025-09-12 | 11.4286
01-7320 | Commissioning -Pk9.Final | 2025-08-28 | 2025-09-12 | 11.4286
01-9005 | Commissioning Report Review/App'l -Pk9.Final | 2025-08-06 | 2025-09-12 | 27.1429
01-7314 | OEHS Pre- Walk -Pk9.Final | 2025-09-15 | 2025-09-15 | 0.71429
01-9003 | Punchlist Corrections -Pk9.Final | 2025-08-07 | 2025-09-15 | 28.5714
01-9004 | OEHS Final -Pk9.Final | 2025-09-16 | 2025-09-22 | 5
01-9006 | 100% PSR & OEHS Occ. Sign-Off -Pk9.Final | 2025-09-16 | 2025-09-22 | 5
01-7316 | Final Signoffs -Pk9.Final | 2025-09-23 | 2025-09-23 | 0.71429
Package 10 (P10) - Home Economis, Servery Kiosk Bldg #14
P10 - Submittals
Package 10 - Building B Home Ec, IP Converge & Entry Plaza
Submittals
Installing the Needle Strip Bird Deterrent System on Horizontal Projecting Surfaces - 10296-02
10-10323 | Fabricate - 10296-02 - Pkg 10 | 2025-08-11 | 2025-09-11 | 22.8571
Planting - 329000
32-4404 | LAUSD Review & App'l - 329000 - Pkg 10 | 2024-02-17 | 2025-09-11 | 409.2857
32-10405 | Fabrication - 329000 - Pkg 10 | 2025-09-12 | 2025-09-13 | 1.4286
P10 - Construction
Package 10 - Modernize Home Economics
Treatment of Historic Finishes
10-3102 | Replace Bird Deterrents -West-Pk10-Hist | 2025-09-19 | 2025-09-22 | 2.8571
10-3103 | Replace Bird Deterrents -South-Pk10-Hist | 2025-09-23 | 2025-09-24 | 1.4286
10-3104 | Replace Bird Deterrents -North-Pk10-Hist | 2025-09-25 | 2025-09-26 | 1.4286
Interiors
Level 1
Corridor
Clean/Punch/Commission
01-2201 | Final Clean Up -L1-Pk10-Corr | 2025-09-15 | 2025-09-19 | 3.5714
01-2282 | Punch -L1-Pk10-Corr | 2025-09-22 | 2025-09-26 | 3.5714
Finishes
12-3129 | Install Window Blinds -L1-Pk10-Corr | 2025-09-02 | 2025-09-08 | 5
Restrooms
Clean/Punch/Commission
01-2287 | Final Clean Up -L1-Pk10-RR | 2025-09-15 | 2025-09-19 | 3.5714
01-2293 | Punch -L1-Pk10-RR | 2025-09-22 | 2025-09-26 | 3.5714
Interior - West Bldg (GL A-L, 6-10)
Clean/Punch/Commission
01-2189 | Final Clean Up -L1-Pk10-West | 2025-09-15 | 2025-09-19 | 3.5714
01-2283 | Punch -L1-Pk10-West | 2025-09-22 | 2025-09-26 | 3.5714
Specialties / Equipment
12-3126 | Install Window Blinds -L1-Pk10-West | 2025-09-02 | 2025-09-08 | 5
01-2294 | FF&E -L1-Pk10-West | 2025-09-15 | 2025-09-19 | 3.5714
Interior - East Bldg - North (GL 1-6, K-Q)
Specialties
12-3166 | Install Window Blinds -L1-Pk10-NE | 2025-09-02 | 2025-09-08 | 5
01-2311 | FF&E -L1-Pk10-NE | 2025-09-15 | 2025-09-19 | 3.5714
Clean/Punch/Commission
01-2301 | Final Clean Up -L1-Pk10-NE | 2025-09-15 | 2025-09-19 | 3.5714
01-2307 | Punch -L1-Pk10-NE | 2025-09-22 | 2025-09-26 | 3.5714
Interior - East Bldg - South (GL L-R, 6-10)
Specialties
01-2322 | FF&E -L1-Pk10-SE | 2025-09-15 | 2025-09-19 | 3.5714
Clean/Punch/Commission
01-2312 | Final Clean Up -L1-Pk10-SE | 2025-09-15 | 2025-09-19 | 3.5714
01-2318 | Punch -L1-Pk10-SE | 2025-09-22 | 2025-09-26 | 3.5714
Level 2
Corridor
Frame Ceiling and MEP Drops
09-9609 | Seismic Bracing Installation -L2-Pk10-Corr | 2025-08-13 | 2025-09-02 | 15
Ceiling Finishes
09-5318 | Ceiling Tiles -L2-Pk10-Corr | 2025-06-26 | 2025-09-02 | 49.2857
Equipment/Furnishings
14-2816 | Install Wheelchair Lift -L2-Pk10-Corr | 2025-09-03 | 2025-09-16 | 10
Clean/Punch/Commission
01-2335 | Final Clean Up -L2-Pk10-Corr | 2025-09-15 | 2025-09-19 | 3.5714
01-2342 | Punch -L2-Pk10-Corr | 2025-09-22 | 2025-09-26 | 3.5714
Restrooms
Clean/Punch/Commission
01-2347 | Final Clean Up -L2-Pk10-RR | 2025-09-15 | 2025-09-19 | 3.5714
01-2353 | Punch -L2-Pk10-RR | 2025-09-22 | 2025-09-26 | 3.5714
Interior - West Bldg (GL A-L, 6-10)
Specialties
01-2354 | FF&E -L2-Pk10-West | 2025-09-02 | 2025-09-08 | 5
Clean/Punch/Commission
01-2323 | Final Clean Up -L2-Pk10-West | 2025-09-15 | 2025-09-19 | 3.5714
01-2343 | Punch -L2-Pk10-West | 2025-09-22 | 2025-09-26 | 3.5714
Interior - East Bldg North (GL 1-6, K-Q)
Equipment/Furnishings
12-3177 | Install Window Blinds -L2-Pk10-NE | 2025-09-02 | 2025-09-08 | 5
Specialties
01-2365 | FF&E -L2-Pk10-NE | 2025-09-02 | 2025-09-08 | 5
Clean/Punch/Commission
01-2355 | Final Clean Up -L2-Pk10-NE | 2025-09-15 | 2025-09-19 | 3.5714
01-2361 | Punch -L2-Pk10-NE | 2025-09-22 | 2025-09-26 | 3.5714
Interior - East Bldg South (GL L-R, 6-10)
Equipment/Furnishings
12-3180 | Install Window Blinds -L2-Pk10-SE | 2025-09-02 | 2025-09-08 | 5
Specialties
01-2376 | FF&E -L2-Pk10-SE | 2025-09-02 | 2025-09-08 | 5
Clean/Punch/Commission
01-2366 | Final Clean Up -L2-Pk10-SE | 2025-09-15 | 2025-09-19 | 3.5714
01-2372 | Punch -L2-Pk10-SE | 2025-09-22 | 2025-09-26 | 3.5714
Exterior
Lunch Shelter Upgrades
27-1499 | IP Converge - Lunch Shelter | 2025-08-28 | 2025-09-03 | 5
09-1499 | Exterior Finishes - Lunch Shelter | 2025-09-15 | 2025-09-19 | 3.5714
10-3100 | SS Cable For Bird Netting -Lunch Shelter | 2025-09-15 | 2025-09-19 | 3.5714
10-3101 | Install Bird Netting -Lunch Shelter | 2025-09-17 | 2025-09-23 | 5
05-3110 | Railing - Lunch Shelter | 2025-09-15 | 2025-09-26 | 8.5714
Testing / Sign-offs
HVAC
Start Up/ TAB
32-10505 | IMPACT - NOE - Remobilize / Resume Commissioning | 2025-08-26 | 2025-09-02 | 5.7143
23-9090 | Pre- Functional Checklist -TAB | 2025-05-19 | 2025-09-05 | 78.5714
32-10515 | IMPACT - CCD 091B - Air Distribution to Classrooms | 2025-08-28 | 2025-09-05 | 6.4286
23-9060 | Functional Checklist -TAB | 2025-09-08 | 2025-09-08 | 0.71429
32-10525 | IMPACT - RFC 392.1 - Cannon to Issue CCD-B | 2025-09-08 | 2025-09-12 | 3.5714
23-9100 | TAB Building - TAB | 2025-09-15 | 2025-09-19 | 3.5714
23-9050 | Submit Report-TAB | 2025-10-03 | 2025-10-03 | 0.71429
23-9110 | Generate Trend Report | 2025-09-22 | 2025-10-03 | 8.5714
23-9939 | LAUSD Review and Approval of Report-TAB | 2025-10-06 | 2025-10-17 | 8.5714
Domestic Water
22-2682 | Fixt Hot Water Test-DWtr | 2025-09-09 | 2025-09-11 | 2.1429
Final Sign-offs & Commissioning
26-9020 | JHA Elect Final | 2025-09-02 | 2025-09-08 | 5
22-9026 | JHA Plum Final | 2025-09-12 | 2025-09-18 | 5
21-2869 | 100 % Building & 10% Site Fire Test | 2025-09-17 | 2025-09-22 | 4.2857
01-7024 | FD Final Signoff / Elevator State Inspection | 2025-09-22 | 2025-09-22 | 0.71429
01-7014 | OEHS Pre- Walk | 2025-09-29 | 2025-09-29 | 0.71429
01-8888 | Punchlist Corrections | 2025-09-30 | 2025-10-02 | 2.1429
Gas
22-9285 | Switch Gas from Temp to Main - PKG 10 | 2025-09-02 | 2025-09-08 | 5
Site Work
Landscape
32-4413 | Irrigation Finish -HomeEc.Pk10,LS | 2025-10-06 | 2025-10-14 | 6.4286
32-4415 | Install Trees -HomeEc.Pk10,LS | 2025-10-06 | 2025-10-14 | 6.4286
Finishes
32-3100 | Striping -HomeEc.Pk10,Fin | 2025-09-02 | 2025-09-03 | 1.4286
28-3496 | Exterior Fire Alarm Trim -HomeEc.Pk10,Fin | 2025-09-02 | 2025-09-05 | 2.8571
26-4368 | Exterior Electrical Trim -HomeEc.Pk10,Fin | 2024-11-21 | 2025-09-05 | 206.4286
05-3226 | Guardrail -HomeEc.Pk10,Fin | 2025-09-15 | 2025-09-19 | 3.5714
26-4369 | Set Light Poles on Poured Bases -HomeEc.Pk10,Fin | 2025-09-15 | 2025-09-19 | 3.5714
32-5186 | Precast Concrete Bench -HomeEc.Pk10,Fin | 2025-10-06 | 2025-10-10 | 3.5714
09-5240 | Final Exterior Paint -HomeEc.Pk10,Fin | 2025-10-06 | 2025-10-17 | 8.5714
Utilities
Sewer
33-10159 | IMPACT - LADOT / City Permit Review / BOE Permit | 2025-08-01 | 2025-09-09 | 28.5714
33-3301 | Sewer POC @ Broadway -HomeEc.Pk1-,SS | 2025-09-10 | 2025-09-11 | 1.4286
33-3439 | Backfill Sewer -HomeEc.Pk10,SS | 2025-09-12 | 2025-09-16 | 3.5714
33-3446 | Instl Sewer Drains -HomeEc.Pk1-,SS | 2025-09-12 | 2025-09-18 | 5
Walls / Pads / Misc Concrete
Site Walls
09-5243 | Paint Site Walls -HomeEc.Pk10,StWl | 2025-08-13 | 2025-09-18 | 26.4286
Bio Swale
33-10008 | Install Base & Geotextile Fabric -BioSw-Pk10-StWk | 2025-09-02 | 2025-09-05 | 2.8571
32-9855 | Place Soil -BioSw-Pk10-StWk | 2025-09-08 | 2025-09-09 | 1.4286
05-9280 | Install Grate -BioSw-Pk10-StWk | 2025-09-10 | 2025-09-11 | 1.4286
Ramps
32-10475 | IMPACT - NOE 510 - Waterproofing Exploration - East Ramp | 2025-08-20 | 2025-09-08 | 14.2857
Amphitheater Seating
32-10485 | IMPACT - NOE - Revised Color Selection | 2025-08-06 | 2025-09-02 | 20
32-4436 | Pour Amphitheater Seatings -HomeEc.Pk10,Amp | 2025-09-04 | 2025-09-05 | 1.4286
32-4470 | Cure Amphitheater Seatings -HomeEc.Pk10,Amp | 2025-09-08 | 2025-09-12 | 3.5714
Stairs
32-4439 | Pour Stairs -HomeEc.Pk10,Stair | 2025-09-11 | 2025-09-12 | 1.4286
Hardscape
Flatwork
32-10455 | IMPACT - New Paver Material (CCD __) -HomeEc.Pk10,PCC | 2025-08-19 | 2025-09-02 | 10.7143
32-4452 | Set Pavers -HomeEc.Pk10,PCC | 2025-09-15 | 2025-10-03 | 13.5714
Package 12 (P12) - Admin
P12 - Submittals
Solid State (Led) Lighting - 26 5010
Solid State (Led) Lighting - 26 5010 - Material List
05-10630 | LAUSD Review and Approval - 265010 - Pkg 12 - Material List | 2025-02-07 | 2025-09-01 | 147.8571
Above Ground HVAC Piping - 23 2013
Above Ground HVAC Piping - 23 2013 - Product Data
05-13710 | Prepare and Submit to LAUSD - 232013 - Pkg 12 - Product Data | 2025-08-26 | 2025-09-23 | 20.7143
05-13720 | LAUSD Review and Approval - 232013 - Pkg 12 - Product Data | 2025-09-24 | 2025-10-07 | 10
Hydraulic Elevators - 14 2423
Hydraulic Elevators - 14 2423 - Shop Drawings
05-12300 | Prepare and Submit to LAUSD - 142423 - Pkg 12 | 2025-08-26 | 2025-09-26 | 22.8571
05-12310 | LAUSD Review and Approval - 142423 - Pkg 12 | 2025-09-27 | 2025-10-10 | 10
Package 13 (P13) - Gym, Bridge
P13 - OLD
Package 13 - Modernize Bridge to East Campus
x26-1399 | Safe Off Area - Electrical -Pk13.Bridge | 2025-09-02 | 2025-09-15 | 10
x02-1390 | Sawcut & Remove Concrete @ Ftg -Pk13.Bridge | 2025-09-16 | 2025-09-22 | 5
x03-1390 | Install Added Dowels @ Removed Concrete -Pk13.Bridge | 2025-09-23 | 2025-09-29 | 5
x03-1391 | Repour Concrete @ Added Dowel Location -Pk13.Bridge | 2025-09-30 | 2025-10-06 | 5
x05-1390 | Prep Surface for FRP @ E Pile -Pk13.Bridge | 2025-09-16 | 2025-10-06 | 15
x05-1391 | Install Splay Anchors for FRP @ E Pile -Pk13.Bridge | 2025-09-16 | 2025-10-06 | 15
x26-1391 | Pull Wire to (N) Light Fxt -Pk13.Bridge | 2025-10-07 | 2025-10-13 | 5
x07-1302 | Install (N) Seismic Joint -Pk13.Bridge | 2025-10-07 | 2025-10-13 | 5
x05-1393 | Install 2nd Layer FRP Wrap @ E Pile -Pk13.Bridge | 2025-10-07 | 2025-10-20 | 10
x05-1394 | Prep Surface for FRP @ W Pile -Pk13.Bridge | 2025-10-07 | 2025-10-20 | 10
x05-1395 | Install Splay Anchors for FRP @ W Pile -Pk13.Bridge | 2025-10-07 | 2025-10-20 | 10
x05-1396 | Install 1st Layer FRP Wrap @ W Pile -Pk13.Bridge | 2025-10-07 | 2025-10-20 | 10
x05-1397 | Install 2nd Layer FRP Wrap @ W Pile -Pk13.Bridge | 2025-10-07 | 2025-10-20 | 10
x26-1390 | Extend Lighting Circuits to (E) Panel -Pk13.Bridge | 2025-10-07 | 2025-10-27 | 15
x05-1392 | Install 1st Layer FRP Wrap @ E Pile -Pk13.Bridge | 2025-10-07 | 2025-10-27 | 15
Modernize Gym
Abatement / Demo
xA7220 | Temporary Protection Plan (TPP) implementation / Historic Treatment | 2025-09-30 | 2026-01-19 | 80
P13 - Submittals
Concrete Forming Accessories - 031000
03-2913 | Prepare / Submit Shop Dwgs / Submittals - 031000 - Pkg 13 | 2025-05-16 | 2025-09-08 | 82.8571
03-2915 | Procurement - 031000 - Pkg 13 | 2025-09-09 | 2025-09-09 | 0.71429
03-2916 | Delivery - 031000 - Pkg 13 | 2025-09-10 | 2025-09-10 | 0.71429
Cast-In-Place Concrete - 033000
03-70801 | Prepare / Submit Shop Dwgs / Submittals - 033000 - Pkg 13 | 2025-05-16 | 2025-09-08 | 82.8571
03-70811 | LAUSD Review / Approve Shop Dwgs / Submittals - 033000 - Pkg 13 | 2025-09-09 | 2025-09-22 | 10
03-2923 | Procurement - 033000 - Pkg 13 | 2025-09-23 | 2025-09-23 | 0.71429
03-2924 | Delivery - 033000 - Pkg 13 | 2025-09-23 | 2025-09-23 | 0.71429
Structural Steel Framing - 051200
Duct Support Brackets
05-3213 | Prepare / Submit Shop Dwgs / Submittals - 051200 - Pkg 13 (Duct Support Brackets) | 2025-04-17 | 2025-09-08 | 103.5714
05-3233 | LAUSD Review / Approve Shop Dwgs / Submittals - 051200 - Pkg 13 (Duct Support Brackets) | 2025-04-24 | 2025-09-09 | 99.2857
05-3243 | Fabrication - 051200 - Pkg 13 (Duct Support Brackets) | 2025-09-10 | 2025-10-07 | 20
05-3253 | Delivery - 051200 - Pkg 13 (Duct Support Brackets) | 2025-10-08 | 2025-10-14 | 5
Metal Fabrications - 055000
05-3313 | Procurement - 055000 - Pkg 13 | 2025-07-31 | 2025-09-29 | 43.5714
05-3333 | Delivery - 055000 - Pkg 13 | 2025-09-30 | 2025-10-06 | 5
Finish Carpentry - 062000
06-9071 | Prepare / Submit Shop Dwgs / Submittals - 062000 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
06-2596 | LAUSD Review / Approve Shop Dwgs / Submittals - 062000 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
06-2597 | Procurement - 062000 - Pkg 13 | 2025-09-30 | 2025-12-11 | 52.1429
Architectural Woodwork - 064000
06-9081 | Prepare / Submit Shop Dwgs / Submittals - 064000 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
06-9091 | LAUSD Review / Approve Shop Dwgs / Submittals - 064000 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
06-9101 | Procurement - 064000 - Pkg 13 | 2025-09-30 | 2025-12-11 | 52.1429
Hollow Metal Doors and Frames - 081113
08-9378 | Delivery (readily available when needed)- 081113 - Pkg 13 | 2025-09-02 | 2025-09-08 | 5
Door Hardware - 087100
08-9408 | Delivery (readily available when needed) - 087100 - Pkg 13 | 2025-09-02 | 2025-09-08 | 5
Glazing - 088000
08-4471 | Prepare / Submit Shop Dwgs / Submittals - 088000 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
08-4472 | LAUSD Review / Approve Shop Dwgs / Submittals - 088000 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
08-4473 | Procurement - 088000 - Pkg 13 | 2025-10-06 | 2026-01-30 | 83.5714
Non-Structural Metal Framing - 092216
09-9429 | Delivery (readily available when needed) - 092216 - Pkg 13 - Readily Available | 2025-09-02 | 2025-09-08 | 5
Historical Elements Preservation
09-5184 | Prepare / Submit Shop Dwgs / Submittals - Historical Elements - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
09-5185 | LAUSD Review / Approve Shop Dwgs / Submittals - Historical Elements - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
09-5186 | Procurement - Historical Elements - Pkg 13 (Readily Available) | 2025-10-06 | 2025-10-31 | 18.5714
Heavy Duty Quartz Vinyl Tile - 096526
09-9509 | Prepare / Submit Shop Dwgs / Submittals - 096526 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
09-9519 | LAUSD Review / Approve Shop Dwgs / Submittals - 096526 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
09-5206 | Procurement - 096526 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Signage - 101400
10-10083 | Prepare / Submit Shop Dwgs / Submittals - 101400 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
10-10093 | LAUSD Review / Approve Shop Dwgs / Submittals - 101400 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
10-3465 | Procurement - 101400 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Phenolic Toilet Compartments - 102113
10-10103 | Prepare / Submit Shop Dwgs / Submittals - 102113 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
10-10113 | LAUSD Review / Approve Shop Dwgs / Submittals - 102113 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
10-3477 | Procurement - 102113 - Pkg 13 | 2025-09-30 | 2025-11-10 | 30
Cubicle and Shower Curtains - 102123
10-3479 | Prepare / Submit Shop Dwgs / Submittals - 102123 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
10-3480 | LAUSD Review / Approve Shop Dwgs / Submittals - 102123 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
10-3481 | Procurement - 102123 - Pkg 13 | 2025-09-30 | 2025-10-27 | 20
Hand and Hair Dryers - 102815
10-10163 | Delivery (Readily Available when needed) - 102815 - Pkg 13 | 2025-09-02 | 2025-09-08 | 5
Metal Lockers - 105113
10-10173 | Prepare / Submit Shop Dwgs / Submittals - 105113 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
10-10183 | LAUSD Review / Approve Shop Dwgs / Submittals - 105113 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
10-3497 | Procurement - 105113 - Pkg 13 | 2025-10-06 | 2026-02-13 | 93.5714
Exterior Entrance Floor Mats and Frames - 124815
12-3151 | Prepare / Submit Shop Dwgs / Submittals - 124815 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
12-3152 | LAUSD Review / Approve Shop Dwgs / Submittals - 124815 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
12-3153 | Procurement - 124815 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Modernize Elevators - 142423
14-2617 | Prepare / Submit Shop Dwgs / Submittals - 142423 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
14-2618 | LAUSD Review / Approve Shop Dwgs / Submittals - 142423 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
14-2619 | Procurement - 142423 - Pkg 13 | 2025-10-06 | 2026-04-13 | 135.7143
Fire-Suppression Sprinkler System - 211313
21-3010 | Procurement - 211313 - Pkg 13 | 2025-07-23 | 2025-09-22 | 44.2857
21-3020 | Delivery - 211313 - Pkg 13 | 2025-09-23 | 2025-09-29 | 5
Plumbing - 221000
22-2679 | Procurement - 221000 - Pkg 13 | 2025-06-17 | 2025-09-09 | 60.7143
22-2680 | Delivery - 221000 - Pkg 13 | 2025-09-10 | 2025-09-16 | 5
HVAC Insulation - 230700
23-9929 | Revise / Resubmit Shop Dwgs / Submittals - 230700 - Pkg 13 | 2025-06-27 | 2025-09-22 | 62.8571
23-2000 | Review / Approve Shop Dwgs / Submittals - 230700 - Pkg 13 | 2025-06-27 | 2025-10-06 | 72.8571
23-2020 | Procurement - 230700 - Pkg 13 | 2025-10-07 | 2025-11-03 | 20
Heating, Ventilating and Air Conditioning Equipment - 238000
Trane Air Handler Unit
23-9359 | Air Handler Unit Procurement Trane Unit (Exhaust Fans)- 238000 - Pkg 13 | 2025-04-25 | 2025-09-29 | 112.8571
23-9819 | Air Handler Unit Delivery Trane Unit (Exhaust Fans) - 238000 - Pkg 13 | 2025-09-30 | 2025-09-30 | 0.71429
AAON Air Handler Unit
23-9809 | Air Handler Unit Procurement AAON Unit- 238000 - Pkg 13 | 2025-09-02 | 2025-12-26 | 82.8571
Fan Coil / Condensing Units
23-9369 | Fan Coil / Condensing Units Procurement - 238000 - Pkg 13 | 2025-09-02 | 2025-10-29 | 41.4286
Panelboards and Signal Terminal Cabinets - 262416
26-9974 | Revise and Resubmit Shop Dwgs / Submittals - 262416 - Pkg 13 | 2025-06-19 | 2025-09-15 | 63.5714
26-9984 | LAUSD Review / Approve Shop Dwgs / Submittals - 262416 - Pkg 13 | 2025-09-16 | 2025-10-03 | 12.8571
26-9734 | Procurement - 262416 - Pkg 13 | 2025-10-06 | 2026-01-30 | 83.5714
Solid State (LED) Lighting - 265010
26-10074 | Revise / Resubmit Shop Dwgs / Submittals - 265010 - Pkg 13 | 2025-08-21 | 2025-09-15 | 18.5714
26-9764 | LAUSD Review / Approve Shop Dwgs / Submittals - 265010 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
26-4352 | Procurement - 265010 - Pkg 13 | 2025-09-30 | 2025-12-26 | 62.8571
Emergency Generator - 263213
26-4486 | Procurement - 263213 - Pkg 13 | 2025-09-02 | 2025-10-13 | 30
Fire Detection and Alarm - 283100
28-10640 | Revise / Resubmit Shop Dwgs / Submittals - 283100 - Pkg 13 | 2025-06-30 | 2025-09-15 | 55.7143
28-10650 | LAUSD Review / Approve Shop Dwgs / Submittals - 283100 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
28-3478 | Procurement - 283100 - Pkg 13 | 2025-09-30 | 2025-10-27 | 20
Carbon Monoxide Detection and Alarm Systems - 283149
28-3480 | Prepare / Submit Shop Dwgs / Submittals - 283149 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
28-3481 | LAUSD Review / Approve Shop Dwgs / Submittals - 283149 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
28-3482 | Procurement - 283149 - Pkg 13 | 2025-09-30 | 2025-10-27 | 20
Portable Water Irrigation - 328413
32-10255 | Prepare / Submit Shop Dwgs / Submittals - 328413 - Pkg 13 | 2025-08-01 | 2025-09-12 | 30.7143
32-10265 | LAUSD Review / Approve Shop Dwgs / Submittals - 328413 - Pkg 13 | 2025-09-13 | 2025-09-26 | 10
32-4397 | Procurement - 328413 - Pkg 13 | 2025-09-29 | 2025-10-24 | 18.5714
Irrigation Controls - 328416
32-4399 | Prepare / Submit Shop Dwgs / Submittals - 328416 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
32-4400 | LAUSD Review / Approve Shop Dwgs / Submittals - 328416 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
32-4401 | Procurement - 328416 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Planting - 329000
32-10266.0 | Prepare / Submit Shop Dwgs / Submittals - 329000 - Pkg 13 | 2025-08-01 | 2025-09-12 | 30.7143
32-10266 | LAUSD Review / Approve Shop Dwgs / Submittals - 329000 - Pkg 13 | 2025-09-13 | 2025-09-26 | 10
32-10266.1 | Procurement - 329000 - Pkg 13 | 2025-09-29 | 2025-10-24 | 18.5714
Site Water Distribution Systems - 331100
33-10049 | Revise / Resubmit Shop Dwgs / Submittals - 331100 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
33-10059 | LAUSD Review / Approve Shop Dwgs / Submittals - 331100 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
33-3413 | Procurement - 331100 - Pkg 13 | 2025-09-30 | 2025-10-06 | 5
33-3414 | Delivery - 331100 - Pkg 13 | 2025-10-07 | 2025-10-07 | 0.71429
Site Sanitary Sewer Utilities - 333000
33-10069 | Prepare / Submit Shop Dwgs / Submittals - 333000 - Pkg 13 | 2025-08-01 | 2025-09-15 | 32.8571
33-10079 | LAUSD Review / Approve Shop Dwgs / Submittals - 333000 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
33-3417 | Procurement - 333000 - Pkg 13 | 2025-09-30 | 2025-10-06 | 5
33-3418 | Delivery - 333000 - Pkg 13 | 2025-10-07 | 2025-10-07 | 0.71429
Seismic Curb - 230548
05-13700 | Prepare / Submit Shop Dwgs / Submittals - 230548 - PKG 13 | 2025-08-01 | 2025-10-10 | 50.7143
05-13690 | Review / Approve Shop Dwgs / Submittals - 230548 - PKG 13 | 2025-10-11 | 2025-10-24 | 10
Polyvinyl-Chloride Roofing - 075419
08-9608 | Prepare / Submit Shop Dwgs / Submittals - 075419 - Pkg 13 | 2025-02-20 | 2025-09-19 | 151.4286
08-9618 | LAUSD Review / Approve Shop Dwgs / Submittals - 075419 - Pkg 13 | 2025-09-20 | 2025-10-03 | 10
08-9628 | Procurement & Delivery - 075419 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Roofing and Deck Insulation - 072200
08-9648 | LAUSD Review / Approve Shop Dwgs / Submittals - 072200 - Pkg 13 | 2025-07-31 | 2025-09-01 | 23.5714
08-9658 | Procurement & Delivery - 072200 - Pkg 13 | 2025-09-02 | 2025-09-29 | 20
Visual Display Units - 101100
10-10094.0 | Prepare / Submit Shop Dwgs / Submittals - 101100 - Pkg 13 | 2025-07-07 | 2025-09-02 | 41.4286
10-10094 | LAUSD Review / Approve Shop Dwgs / Submittals - 101100 - Pkg 13 | 2025-09-03 | 2025-09-16 | 10
10-10094.1 | Procurement - 101100 - Pkg 13 | 2025-09-17 | 2025-10-14 | 20
Formed Metal Wall Panels - 074213.13
07-10175 | Prepare / Submit Shop Dwgs / Submittals - 074213.13 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
07-1010 | Review / Approve Shop Dwgs / Submittals - 074213.13 - Pkg 13 | 2025-09-22 | 2025-10-03 | 8.5714
07-10185 | Procurement - 074213.13 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Flashing and Sheet Metal - 076000
07-10205 | Prepare / Submit Shop Dwgs / Submittals - 076000 - Pkg 13 | 2025-08-01 | 2025-09-19 | 35.7143
07-1030 | Review / Approve Shop Dwgs / Submittals - 076000 - Pkg 13 | 2025-09-22 | 2025-10-03 | 8.5714
07-10215 | Procurement - 076000 - Pkg 13 | 2025-10-06 | 2025-10-31 | 18.5714
Painting and Coating - 099000
09-9990 | Review / Approve Shop Dwgs / Submittals - Painting - Pkg 13 | 2025-07-29 | 2025-09-02 | 25.7143
09-10010 | Procurement - Painting - Pkg 13 | 2025-09-03 | 2025-09-30 | 20
09-10020 | Delivery - Painting - Pkg 13 | 2025-10-01 | 2025-10-07 | 5
Environmental Controls and Energy Management Systems - 230923
23-3010 | Procurement - 230923 - Pkg 13 | 2025-08-25 | 2025-09-02 | 6.4286
23-3011 | Delivery - 230923 - Pkg 13 | 2025-09-03 | 2025-09-03 | 0.71429
Premises Wiring for Convergence of Communication Systems - 271015
27-10691 | Prepare / Submit Shop Dwgs / Submittals - 271015 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
27-2000 | Review / Approve Shop Dwgs / Submittals - 271015 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
27-10701 | Procurement - 271015 - Pkg 13 | 2025-09-30 | 2025-10-27 | 20
Converged IP Public Address and Intercommunication Systems - 275117
27-10761 | Procurement - 275117 - Pkg 13 | 2025-08-25 | 2025-09-29 | 25.7143
27-10771 | Delivery - 275117 - Pkg 13 | 2025-09-30 | 2025-10-06 | 5
Clock and Program Systems - 275313
27-10781 | Prepare / Submit Shop Dwgs / Submittals - 275313 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
27-2021 | Review / Approve Shop Dwgs / Submittals - 275313 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
27-10791 | Procurement - 275313 - Pkg 13 | 2025-09-30 | 2025-10-27 | 20
Classroom Sound Enhancement System - 274113
27-10721 | Prepare / Submit Shop Dwgs / Submittals - 274113 - Pkg 13 | 2025-08-25 | 2025-09-15 | 15.7143
27-2013 | Review / Approve Shop Dwgs / Submittals - 274113 - Pkg 13 | 2025-09-16 | 2025-09-29 | 10
27-10731 | Procurement - 274113 - Pkg 13 | 2025-09-30 | 2025-10-27 | 20
P13 - Construction
Abatement / Demolition
Demolition / Abatement
Roof
C-43 | Demolition - Roof | 2025-06-09 | 2025-09-12 | 68.5714
C-43.1 | IMPACT - Added DSA Scope - Demolition - Roof | 2025-09-15 | 2025-09-19 | 3.5714
Exterior
C-1853.1 | IMPACT - Added DSA Scope - Demolition - Exterior | 2025-09-02 | 2025-09-15 | 10
C-1883 | Abatement - Exterior | 2025-09-16 | 2025-09-22 | 5
C-1883.1 | IMPACT - Added DSA Scope - Abatement - Exterior | 2025-09-23 | 2025-10-06 | 10
Interior Buildout
C-5000 | Existing Elevator Upgrades | 2025-10-06 | 2025-10-10 | 3.5714
Level 1
Structural / Concrete / Underslab MEP
C-103.1 | IMPACT - Added DSA Scope - Sawcut Slab - Level 1 | 2025-08-29 | 2025-09-03 | 4.2857
C-113 | Underslab Plumbing - Level 1 | 2025-09-04 | 2025-09-10 | 5
C-113.1 | IMPACT - Added DSA Scope - Underslab Plumbing - Level 1 | 2025-09-11 | 2025-09-17 | 5
C-133 | Patch Concrete Slab on Grade - Level 1 | 2025-09-18 | 2025-09-24 | 5
C-133.1 | IMPACT - Added DSA Scope - Patch Concrete Slab on Grade - Level 1 | 2025-09-25 | 2025-10-01 | 5
C-143 | Form / Reinforce / Pour - Concrete Curbs (Lockers / Bathrooms etc) / Pads (Equipment etc) - Level 1 | 2025-10-02 | 2025-10-08 | 5
C-143.2 | Reinforce - Concrete Curbs (Lockers/Bathrms) / Pads (Equip) - Level 1 | 2025-10-02 | 2025-10-08 | 5
C-143.1 | IMPACT - Added DSA Scope - Form / Reinforce / Pour - Concrete Curbs / Pads - Level 1 | 2025-10-09 | 2025-10-29 | 15
Roof
C-950 | Plumbing Fixtures / Piping - Roof | 2025-09-22 | 2025-09-26 | 3.5714
C-543 | Install Support Steel - Roof | 2025-09-22 | 2025-10-10 | 13.5714
C-2233 | Screen Wall Supports - Roof | 2025-09-22 | 2025-10-10 | 13.5714
Converged IP Public Address and Intercommunication Systems
27-2019 | PA Device Install | 2025-09-02 | 2025-09-08 | 5
27-2020 | Testing/Commissioning | 2025-09-09 | 2025-09-15 | 5
Exterior
Site
Demo
C-1453 | Construction Fence | 2025-09-02 | 2025-09-03 | 1.4286
C-1233 | Demo Ex. UG Utilities | 2025-09-04 | 2025-09-08 | 3.5714
Grading
C-1083 | Grading / Excavation | 2025-09-09 | 2025-09-10 | 1.4286
C-3653 | IMPACT - Added DSA Scope - Grading / Excavation | 2025-09-11 | 2025-09-12 | 1.4286
C-1093 | Form / Reinforce / Pour - Switchback Ramp Retaining / Cheek Wall Foundations | 2025-09-15 | 2025-09-23 | 6.4286
C-3663 | IMPACT - Added DSA Scope - Form / Reinforce / Pour - Switchback Ramp Retaining / Cheek Wall Foundations | 2025-09-24 | 2025-10-02 | 6.4286
C-2533 | Form / Reinforce / Pour - Switchback Ramp Retaining Cheek Walls | 2025-10-03 | 2025-10-13 | 7.8571
Hardscape
C-2243.1 | Reinforce - Light Pole Bases - Site | 2025-09-02 | 2025-09-08 | 5
Fire Pump Room (From Package 5)
C-1463 | Fire Riser | 2025-09-04 | 2025-09-10 | 5
C-2283 | Underground Electrical | 2025-09-11 | 2025-09-17 | 5
C-2293 | Underground Plumbing | 2025-09-11 | 2025-09-17 | 5
C-2303 | Equipment Pads | 2025-09-18 | 2025-09-24 | 5
C-2313 | Set Fire Pump | 2025-09-25 | 2025-10-01 | 5
C-2323 | Set Jockey Pump | 2025-09-25 | 2025-10-01 | 5
C-1473 | Electrical Connections from Generator | 2025-10-02 | 2025-10-08 | 5
C-1483 | Low Voltage Connections from Generator | 2025-10-09 | 2025-10-15 | 5
Bridge
C-1723 | Structural Improvements (Dowel / Drill / Epoxy / Rebar) | 2025-08-25 | 2025-09-08 | 10.7143
C-2273 | Form / Pour - Column Strengthening | 2025-09-09 | 2025-09-15 | 5
C-1663 | Patch Concrete | 2025-09-16 | 2025-09-22 | 5
C-8453 | Backfill | 2025-09-23 | 2025-09-25 | 2.1429
C-1653 | Seismic Joint (Pkg 14 Tower Complete - Predecessor) | 2025-09-26 | 2025-10-02 | 5
C-1683 | Lighting Conduit | 2025-09-26 | 2025-10-02 | 5
C-1693 | Pull Wire | 2025-10-03 | 2025-10-09 | 5
C-1673 | FPU Panels at Masts | 2025-10-10 | 2025-10-16 | 5
Package 14 (P14) - New Classroom Building w Elevator
P14 - Submittals
Package 14 - Bldg H - New Classroom Building
Submittals
Architectural Woodwork - 064000
06-2119 | Fabrication - 064000 - Pkg 14 | 2025-09-02 | 2025-11-10 | 50
Metal Wall Panels - 074213
Metal Wall Panels - 074213 - Shop Drawings
07-2510 | Fabrication - 074213 - Pkg 14 | 2025-07-11 | 2025-09-18 | 50
07-2511 | Delivery - 074213 - Pkg 14 | 2025-09-19 | 2025-09-19 | 0.71429
Mineral Fiber-Reinforced Cementitious Panels - 074456
07-10125 | Material Lead Time - 074456 - Pkg 14 | 2025-05-30 | 2025-09-08 | 72.8571
07-4103 | Delivery - 074456 - Pkg 14 | 2025-09-09 | 2025-09-09 | 0.71429
Interior Expansion Joint Cover Assemblies - 079513.13
07-10055 | Prepare and Submit to LAUSD - 079513.13 - Pkg 14 | 2025-03-03 | 2025-09-19 | 143.5714
07-4105 | LAUSD Review & App'l - 079513.13 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
07-4106 | Fabrication - 079513.13 - Pkg 14 | 2025-10-06 | 2025-10-31 | 18.5714
Exterior Expansion Joint Cover Assemblies - 079513.16
07-9965 | Prepare and Submit to LAUSD - 079513.16 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
07-4109 | LAUSD Review & App'l - 079513.16 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
07-4110 | Fabrication - 079513.16 - Pkg 14 | 2025-10-06 | 2025-10-31 | 18.5714
Coiling Counter Doors
08-P14130 | Fabrication - 083313 - Pkg 14 | 2025-08-25 | 2025-09-30 | 26.4286
08-P14140 | Delivery - 083313 - Pkg 14 | 2025-10-01 | 2025-10-07 | 5
Overhead Coiling Doors
08-P14150 | Fabrication - 083323 - Pkg 14 | 2025-08-25 | 2025-09-30 | 26.4286
08-P14160 | Delivery - 083323 - Pkg 14 | 2025-10-01 | 2025-10-07 | 5
Security Glazing - 088053
08-2295 | Fabrication - 088053 - Pkg 14 | 2025-08-25 | 2025-09-29 | 25.7143
08-2296 | Delivery - 088053 - Pkg 14 | 2025-09-30 | 2025-10-06 | 5
Moisture Testing for Flooring Installation - 090565
09-9589 | Prepare and Submit to LAUSD - 090565 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
09-6770 | LAUSD Review & App'l - 090565 - Pkg 14-Readily available | 2025-01-20 | 2025-10-03 | 183.5714
Ceramic Tiling - 093013
09-2315 | Fabrication - 093013 - Pkg 14 | 2025-05-28 | 2025-09-29 | 89.2857
Visual Display Units - 101100
10-10263 | Prepare and Submit to LAUSD - 101100 - Pkg 14 | 2025-01-20 | 2025-09-05 | 163.5714
10-2386 | LAUSD Review & App'l - 101100 - Pkg 14 | 2025-01-20 | 2025-09-19 | 173.5714
10-2387 | Fabrication - 101100 - Pkg 14 | 2025-09-22 | 2025-10-17 | 18.5714
Signage - 101400
10-10273 | Prepare and Submit to LAUSD - 101400 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
10-2390 | LAUSD Review & App'l - 101400 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
10-2391 | Fabrication - 101400 - Pkg 14 | 2025-10-06 | 2025-10-31 | 18.5714
Metal Lockers - 105113
10-2423 | Fabrication - 105113 - Pkg 14 | 2025-06-24 | 2025-10-10 | 77.8571
Steel Storage Assemblies - 105613
10-10283 | Prepare and Submit to LAUSD - 105613 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
10-2426 | LAUSD Review & App'l - 105613 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
10-2427 | Fabrication - 105613 - Pkg 14 | 2025-10-06 | 2025-12-03 | 42.1429
Metal Book Shelving MS & HS Text Book Rooms - 105616
10-10293 | Prepare and Submit to LAUSD - 105616 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
10-2442 | LAUSD Review & App'l - 105616 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
10-2443 | Fabrication - 105616 - Pkg 14 | 2025-10-06 | 2025-12-03 | 42.1429
Mobile Storage Shelving - 105626
10-2435 | Fabrication - 105626 - Pkg 14 | 2025-05-02 | 2025-09-02 | 88.5714
Laboratory Equipment - 115300
11-2455 | Fabrication - 115300 - Pkg 14 | 2025-07-31 | 2025-10-03 | 46.4286
11-2456 | Delivery - 115300 - Pkg 14 | 2025-10-06 | 2025-10-10 | 3.5714
Roller Window Shades - 122113
12-8042 | Prepare and Submit to LAUSD - 122113 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
12-2478 | LAUSD Review & App'l - 122113 - Pkg 14 | 2025-01-20 | 2025-10-03 | 183.5714
12-2479 | Fabrication - 122113 - Pkg 14 | 2025-10-06 | 2025-11-17 | 30.7143
Wood Laboratory Casework - 123553
12-3620 | Fabrication - 123553 - Pkg 14 | 2025-09-02 | 2025-11-25 | 60.7143
Bicycle Racks - 129313
12-2503 | Fabrication - 129313 - Pkg 14 | 2025-05-01 | 2025-09-02 | 89.2857
Parking Lot and Site LED Lighting - 265617
26-9914 | Revise and Resubmit - 265617 - Pkg 14 | 2025-01-27 | 2025-09-03 | 157.1429
26-9924 | LAUSD Review & App'l - 265617 - Pkg 14 | 2025-09-04 | 2025-09-23 | 14.2857
26-2771 | Fabrication - 265617 - Pkg 14 | 2025-09-24 | 2025-11-04 | 30
Access Control System (ACS) - 281000
28-2671 | Fabrication - 281000 - Pkg 14 | 2024-11-01 | 2025-09-02 | 218.5714
Video Monitoring and Surveillance Systems (CCTC) - 282300
28-2697 | Fabrication - 282300 - Pkg 14 | 2025-09-02 | 2025-09-29 | 20
Carbon Monoxide Detection and Alarm Systems - 283149
28-10750 | Prepare and Submit - 283149 - Pkg 14 | 2023-07-19 | 2025-09-15 | 564.2857
28-2682 | LAUSD Review & App'l - 283149 - Pkg 14 | 2025-09-16 | 2025-09-29 | 10
28-2683 | Fabrication - 283149 - Pkg 14 | 2025-09-30 | 2025-10-27 | 20
Chain Link Fences and Gates - 323113
32-P14090 | Prepare and Submit to LAUSD - 323113 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-P14030 | LAUSD Review & App'l - 323113 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
32-P14110 | Fabrication and Delivery - 323113 - Pkg 14 | 2025-10-04 | 2025-11-14 | 30
Ornamental Fencing and Gates - 323116
32-P14100 | Prepare and Submit to LAUSD - 323116 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-P14050 | LAUSD Review & App'l - 323116 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
32-P14120 | Fabrication and Delivery - 323116 - Pkg 14 | 2025-10-04 | 2025-11-28 | 40
Architectural Concrete - 323300
32-P14130 | Prepare and Submit to LAUSD - Precast Conc Benches - Pkg 14 | 2025-04-24 | 2025-09-15 | 103.5714
32-P14060 | LAUSD Review & App'l - Precast Conc Benches - Pkg 14 | 2025-09-16 | 2025-09-29 | 10
Portable Water Irrigation - 328413
32-10325 | Prepare and Submit to LAUSD - 328413 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-2758 | LAUSD Review & App'l - 328413 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
32-2760 | Fabrication and Delivery - 328413 - Pkg 14 | 2025-10-06 | 2025-10-31 | 18.5714
Irrigation Controls - 328416
32-10335 | Prepare and Submit to LAUSD - 328416 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-2762 | LAUSD Review & App'l - 328416 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
32-2764 | Fabrication and Delivery - 328416 - Pkg 14 | 2025-10-06 | 2025-10-31 | 18.5714
Planting - 329000
32-10345 | Prepare and Submit to LAUSD - 329000 - Pkg 14 | 2023-07-19 | 2025-09-19 | 567.1429
32-2766 | LAUSD Review & App'l - 329000 - Pkg 14 | 2025-09-20 | 2025-10-03 | 10
32-10435 | Fabrication and Delivery - 329000 - Pkg 14 | 2025-10-04 | 2025-10-31 | 20
P14 - Construction
Site Work
Utilities
Courtyard
Storm Drain
33-2794 | Install SD Piping -Utl-Pk14-Site | 2025-05-12 | 2025-09-08 | 85.7143
33-2795 | Instl Catch Basins -Utl-Pk14-Site | 2025-05-19 | 2025-09-08 | 80.7143
33-2796 | Instl Divrsn Struct -Utl-Pk14-Site | 2025-05-19 | 2025-09-08 | 80.7143
33-2797 | Instl SD SW Outlts -Utl-Pk14-Site | 2025-05-19 | 2025-09-08 | 80.7143
33-2798 | Test SD -Utl-Pk14-Site | 2025-09-09 | 2025-09-10 | 1.4286
33-2799 | Backfill SD -Utl-Pk14-Site | 2025-09-11 | 2025-09-15 | 3.5714
Fire Water
21-2525 | Exc FW -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
21-2526 | Instl FW Piping -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2527 | FW Thrst Blks -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2528 | Instl FW Bckflw Prvt -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2529 | Instl FW PIV -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2530 | Instl Fire Hydrant -Utl-Pk14-Site | 2025-09-17 | 2025-09-23 | 5
21-2531 | Test FW -Utl-Pk14-Site | 2025-09-24 | 2025-09-25 | 1.4286
21-2532 | Backfill FW -Utl-Pk14-Site | 2025-09-26 | 2025-09-30 | 3.5714
Electrical
26-2607 | Exc/Trnch Elect -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2608 | Instl Elect Line -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2609 | Set Pl Boxs -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2610 | Test Elect Lines -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2611 | Backfill Elect -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2612 | Wall Pen/WP -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2613 | Instl Telecm Lines -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2618 | Set Telecm Vaults -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2615 | Electrical Pathways -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
26-2616 | Telecm Pathways -Utl-Pk14-Site | 2025-09-16 | 2025-09-22 | 5
Building
Roof
06-9011 | Mechnical Screens -Rf-Pk14-Str | 2025-09-02 | 2025-09-15 | 10
23-P14310 | Envi/Enrg Mgm Sys -Roof-Pk14 | 2025-09-02 | 2025-09-15 | 10
Enclosure
West Elevation
Plaster
09-2671 | Scratch -West-Pk14-Ext | 2025-09-12 | 2025-09-18 | 5
09-2676 | Cure -West-Pk14-Ext | 2025-09-19 | 2025-09-20 | 1.4286
09-2672 | Brown Coat -West-Pk14-Ext | 2025-09-22 | 2025-09-25 | 2.8571
09-2677 | Cure -West-Pk14-Ext | 2025-09-26 | 2025-10-02 | 5
09-2673 | Finish Coat -West-Pk14-Ext | 2025-10-03 | 2025-10-09 | 5
09-2678 | Cure -West-Pk14-Ext | 2025-10-10 | 2025-10-11 | 1.4286
South Elevation
Plaster
09-10050 | IMPACT CCD 28A - DSA Review -South-Pk14-Ext | 2025-07-23 | 2025-09-11 | 36.4286
09-10060 | IMPACT CCD 28A - Late DSA Review -South-Pk14-Ext | 2025-08-06 | 2025-09-11 | 26.4286
09-6669 | Scratch -South-Pk14-Ext | 2025-09-12 | 2025-09-18 | 5
09-6673 | Cure -South-Pk14-Ext | 2025-09-19 | 2025-09-20 | 1.4286
09-6670 | Brown Coat -South-Pk14-Ext | 2025-09-22 | 2025-09-26 | 3.5714
09-6674 | Cure -South-Pk14-Ext | 2025-09-27 | 2025-10-03 | 5
09-6671 | Finish Coat -South-Pk14-Ext | 2025-10-06 | 2025-10-10 | 3.5714
09-6675 | Cure -South-Pk14-Ext | 2025-10-11 | 2025-10-12 | 1.4286
East Elevation
Framing
07-4042 | Exterior Waterproof Openings -East-Pk14-Ext | 2025-09-02 | 2025-09-08 | 5
Plaster
09-6676 | Lath -East-Pk14-Ext | 2025-09-12 | 2025-09-18 | 5
09-6677 | Scratch -East-Pk14-Ext | 2025-09-19 | 2025-09-25 | 5
09-6681 | Cure -East-Pk14-Ext | 2025-09-26 | 2025-09-27 | 1.4286
09-6678 | Brown Coat -East-Pk14-Ext | 2025-09-29 | 2025-10-03 | 3.5714
09-6682 | Cure -East-Pk14-Ext | 2025-10-04 | 2025-10-10 | 5
North Elevation
Plaster
09-6684 | Lath -North-Pk14-Ext | 2025-08-08 | 2025-09-25 | 35
09-6685 | Scratch -North-Pk14-Ext | 2025-09-26 | 2025-10-02 | 5
09-6689 | Cure -North-Pk14-Ext | 2025-10-03 | 2025-10-05 | 2.1429
09-6686 | Brown Coat -North-Pk14-Ext | 2025-10-06 | 2025-10-10 | 3.5714
09-6690 | Cure -North-Pk14-Ext | 2025-10-11 | 2025-10-17 | 5
Interiors
Level 1
Corridor (Exterior)
09-1034 | Drywall Ceilings -L1-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
01-2028 | 2Side Screw Off Insp -L1-Pk14-Int | 2025-09-08 | 2025-09-08 | 0.71429
09-1035 | Tape -L1-Pk14-Int | 2025-09-09 | 2025-09-17 | 6.4286
09-1030 | Prime & 1st Coat Paint -L1-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
23-1006 | Envi/Enrg Mgm Sys -L1-Pk14-Int | 2025-09-25 | 2025-10-01 | 5
26-1027 | Lighting Control System -L1-Pk14-Int | 2025-09-25 | 2025-10-01 | 5
26-1028 | PA System -L1-Pk14-Int | 2025-09-25 | 2025-10-01 | 5
26-1029 | Clng Light Fixt -L1-Pk14-Int | 2025-09-25 | 2025-10-01 | 5
28-P14020 | Access Control Cable Rough-in | 2025-09-25 | 2025-10-01 | 5
09-1037 | Final Above Clng Insp -L1-Pk14-Int | 2025-10-02 | 2025-10-02 | 0.71429
09-1026 | Waterproofing -L1-Pk14-Int | 2025-10-03 | 2025-10-09 | 5
09-1039 | Tile DF -L1-Pk14-Int | 2025-10-10 | 2025-10-16 | 5
Restrooms
09-2735 | Waterproofing -L1-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
09-2736 | Install Tile -L1-Pk14-Int | 2025-09-30 | 2025-10-13 | 10
Electrical Room
26-1000 | Elect Panels -L1-Pk14-Int | 2025-08-15 | 2025-09-02 | 13.5714
26-1007 | Motor Control Device -L1-Pk14-Int | 2025-09-03 | 2025-09-04 | 1.4286
27-1004 | Set LV Cabs/Eq -L1-Pk14-Int | 2025-09-03 | 2025-09-05 | 2.1429
00-1402 | Set Electrical Equipment | 2025-09-02 | 2025-09-08 | 5
26-1006 | LV Transformer -L1-Pk14-Int | 2025-09-08 | 2025-09-10 | 2.1429
26-1008 | Pull/Terminate Feeders -L1-Pk14-Int | 2025-09-05 | 2025-09-22 | 12.8571
26-1003 | Pull/Term LV Branch -L1-Pk14-Int | 2025-09-11 | 2025-10-01 | 15
26-1002 | Pull/Term Branch -L1-Pk14-Int | 2025-09-23 | 2025-10-08 | 11.4286
26-1004 | Megger & Grounding Tests -L1-Pk14-Int | 2025-10-09 | 2025-10-15 | 5
IDF Room
27-P14050 | LV Horizontal Copper Rough-in - Level 1 | 2025-09-02 | 2025-09-04 | 2.1429
26-2778 | LV Transformer -L1-Pk14-Int | 2025-09-05 | 2025-09-09 | 3.5714
27-P14070 | LV Term, Label & Test - Level 1 | 2025-09-10 | 2025-09-12 | 2.1429
26-2780 | Pull/Terminate Feeders -L1-Pk14-Int | 2025-09-02 | 2025-09-17 | 11.4286
26-2776 | Pull/Term LV Branch -L1-Pk14-Int | 2025-09-10 | 2025-09-30 | 15
26-2775 | Pull/Term Branch -L1-Pk14-Int | 2025-09-18 | 2025-10-03 | 11.4286
26-2777 | Megger & Grounding Tests -L1-Pk14-Int | 2025-10-06 | 2025-10-10 | 3.5714
Interior - Ceramics Department
01-2014 | 1Side Screw Off Insp -L1-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
21-2542 | RI FSprink Drops -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
26-2637 | RI Elect Drops -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
23-2612 | RI Mech Drops -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
01-2076 | MEPS Drops Insp -L1-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
07-1001 | Insulate Walls & Clngs -L1-Pk14-Int | 2025-09-11 | 2025-09-17 | 5
27-1003 | CATV Mounting Plates -L1-Pk14-Int | 2025-09-18 | 2025-09-18 | 0.71429
09-2819 | Wall Backing -L1-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
01-2015 | Ins/Close Wall Insp -L1-Pk14-Int | 2025-09-25 | 2025-09-25 | 0.71429
09-1009 | Drywall 2Side -L1-Pk14-Int | 2025-09-26 | 2025-10-02 | 5
01-2016 | 2Side Screw Off Insp -L1-Pk14-Int | 2025-10-03 | 2025-10-03 | 0.71429
09-1010 | Tape -L1-Pk14-Int | 2025-10-06 | 2025-10-14 | 6.4286
Interior - Flex Engineering / Textbook Storage
01-2121 | MEPS Drops Insp -L1-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3068 | Insulate Walls & Clngs -L1-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3984 | CATV Mounting Plates -L1-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
09-5040 | Wall Backing -L1-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2117 | Ins/Close Wall Insp -L1-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-P14040 | Drywall 2Side -L1-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
01-2118 | 2Side Screw Off Insp -L1-Pk14-Int | 2025-09-25 | 2025-09-25 | 0.71429
09-5031 | Tape -L1-Pk14-Int | 2025-09-26 | 2025-10-06 | 7.8571
09-5027 | Prime & 1st Coat Paint -L1-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
Interior - Special Ed
21-2570 | RI FSprink Drops -L1-Pk14-Int | 2025-08-25 | 2025-09-02 | 6.4286
26-4225 | RI Elect Drops -L1-Pk14-Int | 2025-08-25 | 2025-09-02 | 6.4286
23-2886 | RI Mech Drops -L1-Pk14-Int | 2025-08-25 | 2025-09-02 | 6.4286
01-2132 | MEPS Drops Insp -L1-Pk14-Int | 2025-09-03 | 2025-09-03 | 0.71429
07-3069 | Insulate Walls & Clngs -L1-Pk14-Int | 2025-09-04 | 2025-09-10 | 5
27-3986 | CATV Mounting Plates -L1-Pk14-Int | 2025-09-11 | 2025-09-11 | 0.71429
09-5055 | Wall Backing -L1-Pk14-Int | 2025-09-11 | 2025-09-17 | 5
01-2128 | Ins/Close Wall Insp -L1-Pk14-Int | 2025-09-18 | 2025-09-18 | 0.71429
09-5045 | Drywall 2Side -L1-Pk14-Int | 2025-09-19 | 2025-09-25 | 5
01-2129 | 2Side Screw Off Insp -L1-Pk14-Int | 2025-09-26 | 2025-09-26 | 0.71429
09-5046 | Tape -L1-Pk14-Int | 2025-09-29 | 2025-10-07 | 6.4286
09-5042 | Prime & 1st Coat Paint -L1-Pk14-Int | 2025-10-08 | 2025-10-14 | 5
Level 2
Corridor (Exterior)
26-4248 | Lighting Control System -L2-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
26-4250 | Clng Light Fixt -L2-Pk14-Int | 2025-08-15 | 2025-09-08 | 17.8571
09-5084 | Final Above Clng Insp -L2-Pk14-Int | 2025-09-09 | 2025-09-09 | 0.71429
01-2149 | MEPS RI Insp -L2-Pk14-Int | 2025-09-09 | 2025-09-09 | 0.71429
09-5075 | Waterproofing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
07-3072 | Insulate Clngs -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
09-5085 | Tile DF -L2-Pk14-Int | 2025-09-30 | 2025-10-06 | 5
26-4247 | Elect Trim & Devices -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
06-2576 | Finish Carpentry -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
21-2577 | FSprink Trim & Devices -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
10-3427 | Fire Ext & Cabs -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
09-5083 | Rubber Base -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
22-2661 | Drinking Fountains -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
28-3927 | Fire Alarm Trim & Devices -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
Restrooms
09-5098 | Waterproofing -L2-Pk14-Int | 2025-09-02 | 2025-09-08 | 5
09-5099 | Install Tile -L2-Pk14-Int | 2025-09-30 | 2025-10-13 | 10
Electrical Room
26-4226 | Elect Panels -L2-Pk14-Int | 2025-08-18 | 2025-09-02 | 11.4286
26-4231 | Motor Control Device -L2-Pk14-Int | 2025-09-03 | 2025-09-04 | 1.4286
27-3987 | Set LV Cabs/Eq -L2-Pk14-Int | 2025-09-03 | 2025-09-05 | 2.1429
26-4230 | LV Transformer -L2-Pk14-Int | 2025-09-08 | 2025-09-10 | 2.1429
26-4232 | Pull/Terminate Feeders -L2-Pk14-Int | 2025-09-05 | 2025-09-22 | 12.8571
26-4228 | Pull/Term LV Branch -L2-Pk14-Int | 2025-09-11 | 2025-10-01 | 15
26-4227 | Pull/Term Branch -L2-Pk14-Int | 2025-09-23 | 2025-10-08 | 11.4286
26-4229 | Megger & Grounding Tests -L2-Pk14-Int | 2025-10-09 | 2025-10-15 | 5
IDF Room
26-4260 | Elect Panels -L2-Pk14-Int | 2025-08-18 | 2025-09-02 | 11.4286
27-P14060 | LV Horizontal Copper Rough-in - Level 2 | 2025-09-02 | 2025-09-04 | 2.1429
26-4264 | LV Transformer -L2-Pk14-Int | 2025-09-03 | 2025-09-05 | 2.1429
27-P14040 | LV Copper/Fiber Backbone Terminations & Testing | 2025-09-05 | 2025-09-09 | 3.5714
27-P14080 | LV Term, Label & Test - Level 2 | 2025-09-10 | 2025-09-12 | 2.1429
26-4266 | Pull/Terminate Feeders -L2-Pk14-Int | 2025-09-03 | 2025-09-18 | 11.4286
26-4262 | Pull/Term LV Branch -L2-Pk14-Int | 2025-09-08 | 2025-09-26 | 13.5714
26-4261 | Pull/Term Branch -L2-Pk14-Int | 2025-09-19 | 2025-10-06 | 12.8571
26-4263 | Megger & Grounding Tests -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
Interior - Art Department
01-2157 | MEPS Drops Insp -L2-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3070 | Insulate Walls & Clngs -L2-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3990 | CATV Mounting Plates -L2-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
09-5109 | Wall Backing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2139 | Ins/Close Wall Insp -L2-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-5061 | Drywall 2Side -L2-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
01-2140 | 2Side Screw Off Insp -L2-Pk14-Int | 2025-09-25 | 2025-09-25 | 0.71429
09-5062 | Tape -L2-Pk14-Int | 2025-09-26 | 2025-10-06 | 7.8571
09-5058 | Prime & 1st Coat Paint -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
Interior - Chemistry
01-2175 | MEPS Drops Insp -L2-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3073 | Insulate Walls & Clngs -L2-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3995 | CATV Mounting Plates -L2-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
09-5125 | Wall Backing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2171 | Ins/Close Wall Insp -L2-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-5115 | Drywall 2Side -L2-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
01-2172 | 2Side Screw Off Insp -L2-Pk14-Int | 2025-09-25 | 2025-09-25 | 0.71429
09-5116 | Tape -L2-Pk14-Int | 2025-09-26 | 2025-10-06 | 7.8571
09-5112 | Prime & 1st Coat Paint -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
Interior - Gen Classroom
01-2186 | MEPS Drops Insp -L2-Pk14-Int | 2025-09-02 | 2025-09-02 | 0.71429
07-3074 | Insulate Walls & Clngs -L2-Pk14-Int | 2025-09-03 | 2025-09-09 | 5
27-3997 | CATV Mounting Plates -L2-Pk14-Int | 2025-09-10 | 2025-09-10 | 0.71429
27-P14250 | AV Cabling - L2 | 2025-09-10 | 2025-09-12 | 2.1429
09-5140 | Wall Backing -L2-Pk14-Int | 2025-09-10 | 2025-09-16 | 5
01-2182 | Ins/Close Wall Insp -L2-Pk14-Int | 2025-09-17 | 2025-09-17 | 0.71429
09-5130 | Drywall 2Side -L2-Pk14-Int | 2025-09-18 | 2025-09-24 | 5
01-2183 | 2Side Screw Off Insp -L2-Pk14-Int | 2025-09-25 | 2025-09-25 | 0.71429
09-5131 | Tape -L2-Pk14-Int | 2025-09-26 | 2025-10-06 | 7.8571
09-5127 | Prime & 1st Coat Paint -L2-Pk14-Int | 2025-10-07 | 2025-10-13 | 5
Testing / Sign-offs
New Classroom Permanent Power for Elevator
00-1403 | Wiring for Main Electric Equipment / Bollards | 2025-09-09 | 2025-09-22 | 10
Electrical Start-up
Permanent Power
26-2001 | Complete House & E Pwr Risers-PPwr | 2025-09-02 | 2025-09-02 | 0.71429
Elevator
Elevator Machine Room
09-1021 | Tape -L1-Pk14-Int | 2025-08-14 | 2025-09-08 | 18.5714
09-1016 | Sealed Conc Floors -L1-Pk14-Int | 2025-09-09 | 2025-09-11 | 2.1429
Package 15 (P15) - New M&O, Solar, Parking Lot, Horticulture
P15 - Construction
New
Hardscape & Landscaping
Parking Lots
A102400 | Remove Interim Housing - Below Grade - West (Phase 6) | 2025-09-01 | 2025-09-10 | 7.1429
A102410 | Subgrade Prep | 2025-09-11 | 2025-09-15 | 3.5714
Package 16 (P16) - Non-DSA Betterment Package
P16 - Construction
Federal Building
Summer 2025
09-P160030 | Paint (e) Casework - Federal Bldg - Level 1 | 2025-09-02 | 2025-09-08 | 5
09-P160040 | Paint (e) Casework - Federal Bldg - Level 2 | 2025-09-09 | 2025-09-15 | 5
12-P160050 | Install (n) Window Blinds - Federal Bldg - Level 1 | 2025-09-09 | 2025-09-15 | 5
09-P160070 | Paint (e) Metal Lockers - Federal Bldg - Level 1 | 2025-09-09 | 2025-09-15 | 5
12-P160060 | Install (n) Window Blinds - Federal Bldg - Level 2 | 2025-09-16 | 2025-09-22 | 5
09-P160080 | Paint (e) Metal Lockers Federal Bldg - Level 2 | 2025-09-16 | 2025-09-22 | 5
09-P160090 | Paint Exterior Wall - Federal Building | 2025-09-09 | 2025-09-29 | 15
09-P160100 | Remove, Refurbish and Reinstall Security Metal Screens- Federal Building | 2025-09-30 | 2025-10-20 | 15
Music Building
Summer 2025
09-P160110 | Paint (e) Casework - Music Building | 2025-09-02 | 2025-09-08 | 5
Auditorium
Summer 2025
09-P160180 | Paint Exterior Wall - North - Auditorium | 2025-09-02 | 2025-09-08 | 5
09-P160190 | Paint Exterior Wall - South - Auditorium | 2025-09-09 | 2025-09-22 | 10
09-P160200 | Paint Exterior Wall - West - Auditorium | 2025-09-23 | 2025-09-29 | 5
09-P160210 | Paint Exterior Wall - East- Auditorium | 2025-09-30 | 2025-10-06 | 5
Phase 6 Final Construction
New Batting Cages
02-5050 | Site Demo -Pk2.NFH (Batting Cage Pending) | 2023-09-05 | 2025-09-03 | 521.4286
02-2880 | Clear & Grub Site -Pk2.NFH (Batting Cage Pending) | 2023-08-28 | 2025-09-04 | 527.8571
[5 empty] | Lincoln High School - LIVE FILE - TRUE LIVE FILE | [24 empty] | © 2025 XER2XLSXGANTT

## View Settings
VIEW CONFIGURATION SUMMARY
XER2XLSXGANTT © 2025 |  | Printed: 01/12/2026 08:56:27 PM
GENERAL STATISTICS
Project/Baseline | Number of Activities | DD
Lincoln High School - LIVE FILE - TRUE LIVE FILE | 806 | 09/01/2025 07:00
GENERATION STATISTICS
Total views processed | 2
Total view generation time (s) | 48.31
Average view generation time (s) | 24.16
Estimated time (s) | 278.4
Delta (s) | -230.09
View | Activities | Baselines | Generation Time (s) | Rows/Second
View 1: 3 Week Look Ahead | 586 | 0 | 17.71 | 33.08
View 2: 6 Week Look Ahead (D | 806 | 0 | 30.6 | 26.34
View 1: 3 Week Look Ahead
GANTT CHART OPTIONS
Include Gantt Chart | Yes
Time Interval | Day | Identify Weekends | Yes
Weekend Color | #F2F2F2 | Text Angle | 90°
Header Background Color | #808080 | Header Font Color | #FFFFFF
Timeline Range Mode | Manual | Timeline Start | 2025-08-25
Timeline End | 2025-09-22 | Show DD Line | Yes
DD Line Color | #FF0000 | Activity Color Mode | Status Based
Baseline Options
Include Baseline Data | No
Selected Baselines | All
Baseline Color Mode | grey-scale | Baseline 1 Color | #808080
Baseline 2 Color | #A0A0A0 | Baseline 3 Color | #C0C0C0
Header & Footer Options
Include Header | Yes | Header Sections | 3
Include Footer | Yes | Footer Sections | 3
TABLE OPTIONS
Include WBS | Yes
Hide Empty WBS | Yes
WBS Color Mode | Default
WBS Colors | 10 configured
Show Hours/Minutes | No
Show Decimals | No
Date Format | MM/DD/YYYY
Freeze Panes | Yes
WBS Rollup Behavior | Filter Only
Activity Bar Options
Activity Bar Border | No
Activity Bar Merge Cells | No
Show Activity Bar Text | No
WBS Bar Options
WBS Bar Border | No
WBS Bar Merge Cells | No
FILTERS
Filter 1 | start_date between 2025-09-01 and 2025-09-22
Filter 2 | OR finish_date between 2025-09-01 and 2025-09-22
SELECTED COLUMNS
activity_id | task_name | start_date | finish_date
duration
SORTING
Priority | Column | Direction
1 | Finish Date | ASC
View 2: 6 Week Look Ahead (D
GANTT CHART OPTIONS
Include Gantt Chart | Yes
Time Interval | Day | Identify Weekends | Yes
Weekend Color | #f2f2f2 | Text Angle | 90°
Header Background Color | #808080 | Header Font Color | #ffffff
Timeline Range Mode | Manual | Timeline Start | 2025-08-25
Timeline End | 2025-10-13 | Show DD Line | Yes
DD Line Color | #ff0000 | Activity Color Mode | Status Based
Baseline Options
Include Baseline Data | No
Selected Baselines | All
Baseline Color Mode | grey-scale | Baseline 1 Color | #808080
Baseline 2 Color | #a0a0a0 | Baseline 3 Color | #c0c0c0
Header & Footer Options
Include Header | Yes | Header Sections | 3
Include Footer | Yes | Footer Sections | 3
TABLE OPTIONS
Include WBS | Yes
Hide Empty WBS | Yes
WBS Color Mode | Default
WBS Colors | 10 configured
Show Hours/Minutes | No
Show Decimals | No
Date Format | MM/DD/YYYY
Freeze Panes | Yes
WBS Rollup Behavior | Filter And Collapse
Activity Bar Options
Activity Bar Border | No
Activity Bar Merge Cells | No
Show Activity Bar Text | No
WBS Bar Options
WBS Bar Border | No
WBS Bar Merge Cells | No
FILTERS
Filter 1 | start_date between 2025-09-01 and 2025-10-13
Filter 2 | OR finish_date between 2025-09-01 and 2025-10-13
SELECTED COLUMNS
activity_id | task_name | start_date | finish_date
duration
SORTING
Priority | Column | Direction
1 | Finish Date | ASC